Table of Contents

1.0 STRATEGIC OVERVIEW OF AWUTU SENYA DISTRICT ASSEMBLY	3

1.1 LEGISLATIVE ESTABLISHMENT	3

1.2 POPULATION/ DEMOGRAPHY	3

1.3 POLITICAL GOVERNANCE STRUCTURE	3

2.0 DISTRICT ECONOMY	3

2.1 AGRICULTURE	3

2.2 ROAD NETWORK/TRANSPORT	4

2.3 EDUCATION	4

2.4 HEALTH	4

2.5 ENVIRONMENT	5

2.6 TOURISM	5

3.0 KEY DEVELOPMENT PROBLEMS/ISSUES	6

4.0 ADOPTED POLICY OBJECTIES	7

4.0  VISION	7

5.0 GOAL / MISSION STATEMENT	7

6.0 CORE FUNCTIONS OF THE ASSEMBLY	8

7.0 FINANCIAL PERFORMANCE	9

7.1 FINANCIAL PERFORMANCE - REVENUE	9

7.2 FINANCIAL PERFORMANCE-EXPENDITURE	12

8.0 NON FINANCIAL PERFORMANCE BY PROGRAMME	15

8.1 KEY ACHIEVEMENTS (2020)	16

8.2 POLICY OUTCOME INDICATORS AND TARGETS	20

8.3 KEY PERFORMANCE INFORMATION FOR BUDGET PROGRAMMES	21

8.4 2020 BUDGET PROGRAMME PERFORMANCE	23

9.0 FINANCIALS	24

9.1 2020 KEY PROJECTS AND PROGRAMMES FROM ALL SOURCES	24

9.2 SANITATION BUDGET PERFORMANCE	25

9.3 GOVERNMENT FLAGSHIP PROJECTS/PROGRAMMES	26

OUTLOOK FOR 2021-2024	27

10.0 DISTRICT ADOPTED POLICY OBJECTIVES FOR 2021	28

11.0 POLICY OUTCOME INDICATORS AND TARGETS	29

12.0 2021-2024 REVENUE PROJECTIONS	31

12.1 2021-2024 REVENUE PROJECTIONS – IGF ONLY	31

12.2 REVENUE PROJECTION- ALL REVENUE SOURCES	32

13.0 EXPENDITURE BY BUDGET PROGRAMME AND ECONOMIC CLASSIFICATION -ALL FUNDING SOURCES	34

14.0 KEY PERFORMANCE INFORMATION FOR BUDGET PROGRAMMES	35

15.0 2021 EXPENDITURE BY BUDGET PROGRAMME, PROJECTS AND ECONOMIC CLASSIFICATION	37

16.0 GOVERNMENT FLAGSHIP PROJECTS/PROGRAMMES FOR 2021 	39

17.0 2021-2024 EXPENDITURE PROJECTIONS BY ECONOMIC CLASSIFICATION- ALL FUNDING SOURCES	39

18.0 SUMMARY OF EXPENDITURE BUDGET BY DEPARTMENT, ITEM AND FUNDING SOURCES-2021	40

19.0 PROJECTS AND PROGRAMS FOR 2021 AND CORRESPONDING COST AND JUSTIFICATION	41

20.0 SANITATION BUDGET FOR 2021	57

21.0 COMPENSATION OF EMPLOYEES(SUMMARY)	58

1.0 STRATEGIC OVERVIEW OF AWUTU SENYA DISTRICT ASSEMBLY

## 1.1 Legislative Establishment

The Awutu Senya District Assembly was established on 6th February, 2012 by Legislative Instrument (LI 2024). The administrative capital of the District is Awutu Beraku.

## 1.2 Population/ Demography

The 2010 Population and Housing Census estimated the population of the District to be

86,884, accounting for 3.9 percent of the population of the Central Region. About 47.1 percent (40,903) of the population are Males while 52.9 percent (45,981) are Females.

Using a growth rate of 3.1%, the 2021 population of the District is projected at 125,327. Representing 59,029 (47.1%) Males and 66,298 (52.9%) Female.

## 1.3 Political Governance Structure

The Awutu Senya District Assembly has Twenty four (24) Electoral Areas and one Constituency. It has a General Assembly (GA) Membership of (37) comprising 24 Elected Members, 11 Government Appointees in addition to the Hon. DCE and the Hon. MP. Representing 5(14%) Females and 32(86%) Males.

The Assembly has six (6) sub-structures which consists of Senya Urban Council, Awutu, , Obrachire, Bawjiase, Bontrase, and Jei-Krodua Area Councils. These sub-structures are supported by 24 Unit Committees.

# 2.0 DISTRICT ECONOMY

The District is richly endowed with human and natural resources, forest and timber species, rich soil, good climatic conditions and particularly mineral deposits such as gold, diamond and kaolin. It also has diverse occupational structure.  However, the informal sector takes the majority of the employed population with the formal sector absorbing the rest.

## 2.1 Agriculture

The main economic activity in the District is agriculture (fishing and farming) and agro-processing.  Agriculture (including Fishing) and its related activities employ about 56% of the working population in the district. The District has a very good potential for irrigation farming. The District can boast of the Ayensu, Kwekude River and dam, Okurudu stream.

However, there is the need for the district to undertake measures to utilize this potential.

The northern portion of the district is suitable for pineapple and vegetable production. There

are large and medium scale farmers who produce pineapple for export.

## 2.2 Road Network/Transport

The major roads in the district are the section of the Accra - Cape Coast (N1); The Kasoa - Bawjiase road; The Awutu – Obrachire road. There are other feeder roads that link and facilitate movement of people in the district but are only motorable in the dry season. However, periodic reshaping is done to keep the roads motorable all season. The road network available is summarized in the table below:

| Road type | Length | Remarks |
| --- | --- | --- |
| First class | 2km | This is in the domain of Highways |
| Trunk Roads | 14km | 14km need resealing |
| Engineered Feeder Roads | 45km | About 30km requires reshaping and sealing |
| Un-engineered Feeder Roads | About 45km | Requires engineering and reshaping |

## 2.3 Education

The Ghana Education Service superintends the District Education System and a District Education Directorate is situated in Awutu Beraku. The Directorate is made up of eight (8) Circuits namely: Ayensuako, Awutu, Bawjiase (A&B), Bontrase, Obrachire, Senya Beraku and Jei-Krodua. District has 108 Kindergartens/pre-school (61 Private), 149 Primary Schools (88 private) and 106 Junior High Schools (51 private). Obrachire, Senya Beraku and Bawjiase have a Senior High School in each community. However, there are two private Senior High Schools namely; Bontrase Senior Technical School at Bontrase and Awutu Winton Senior High School. Enrolments rates at basic levels have exceeded the 100% marks over the past years due to the district’s proximity to Kasoa and towns of Gomoa East such as Fetteh Kakraba and Akoti.

## 2.4 Health

Health care delivery is facilitated by the District Health Directorate. The District has five (5) Sub-districts, four (4) public health centres located at Bawjiase, Senya, Awutu Beraku, and Bontrase. There are twenty-two (22) functional Community-Based Health Planning Services (CHPS) zones/compounds and Five (5) privately owned health facilities in the District. There is however no hospital and therefore no Doctor. The nurse-patient ratio in the District is 1:908.

## 2.5 Environment

Vegetation in the District can be broadly classified as forest and savannah woodland.

The environment is faced with some challenges, notable among them are: sand winning, bush fires, logging, stone quarrying and inappropriate farming methods which destabilizes the ecosystem.

## 2.6 Tourism

### The District is endowed with historical natural sites which would need some level of marketing and investment (Field Survey, 2014). A historical monument in Senya called the Good Hope Fort is located along the Gulf of Guinea and was built by the Dutch is considered the second Fort/Castle built in the central region of Ghana. Spots of forests in the hinterlands have some natural stone caved feature that needs development and promotion. Forests around Bontrase, Bawuanum, Bosomabena and other areas could be developed with canopy walk ways. The topography of the areas which come in the form of valleys and hills around the forests can also be developed by investors with artificial rivers and golf courses.

# 3.0 KEY DEVELOPMENT PROBLEMS/ISSUES

Like all other District in the Region, the Assembly is saddled with some developmental issues which are summarized in the table below

| 1 | Management And Administration | I. Low revenue outturn largely due to low numbers and capacity of revenue staff. |
| --- | --- | --- |
|  |  | II. Inadequate database for planning and reliable revenue forecasting. |
|  |  | III. Low performance and functioning of zonal councils and unit committees |
|  |  | IV. Local contractors not competitive on national scale due to low capacity. |
|  |  | V. Lack of Assembly owned Land for Projects |
| 2 | Infrastructure Delivery And Management | I. Low coverage of Street naming and property addressing system in the District. |
|  |  | II. Inadequate implementation of building controls and regulations |
|  |  | III. Poor drainage system in some parts of the District capital. |
|  |  | IV. Poor road network in the District |
| 3 | Social Services Delivery | I. Poor quality education due to poor educational infrastructure. |
|  |  | II. Limited ICT skills and knowledge at all levels. |
|  |  | III. Adverse effect of HIV/AIDS/STIs on quality of life and life expectancy of the people. |
|  |  | IV. Inadequate number of Health professionals. |
|  |  | V. Lack of functioning engineered landfills sites. |
|  |  | VI. Inadequate support for victims of domestic violence |
|  |  | VII. Poor sanitation in the District due to inadequate sanitation services. |
|  |  | VIII. Inadequate environmental health personnel |
| 4 | Economic Development | I. Low Agriculture production due to over dependence on rainfall. |
|  |  | II. Low patronage of tourist sites due to inadequate promotion of tourist sites. |
|  |  | III. Inadequate market stalls, sheds and stores in the Awutu Beraku market. |
|  |  | IV. Inadequate Mechanized and large scale farming due to inability to access loan facilities from financial institutions. |
| 5 | Environmental And Sanitation Management | I. Inadequate enforcement of environmental bye-laws |
|  |  | II. Illegal sand winning and logging in the District |

# 4.0 ADOPTED POLICY OBJECTIVES

# Deepen political and administrative Decentralization

- Ensure improved fiscal performance and sustainability

- Deepen Transparency and Public Accountability

- Address recurrent Devastating Floods

- Promote proper maintenance culture

- Promote a Sustainable Spatially Integrated balance and Orderly Development of Human Settlements

- Enhance inclusive and equitable access to, and participation in quality education at all levels.

- Ensure Affordable, Equitable, easily Accessible and Universal Health Coverage (UHC)

- Eradicate Poverty in all its forms and Dimensions

- Ensure  effective child protection and family welfare system

- Strengthen Social protection, especially for children, women, persons with disabilities and the elderly.

- Promote full participation of PWDs in Social and Economic Development of the country

- Improve production efficiency and yield

- Promote a  demand -driven approach to Agricultural development

- Diversify and expand the tourism industry for Economic Development

# 4.0  VISION

## The Awutu Senya District Assembly aspires to become an attractive centre for modernized agriculture, brisk commerce and a knowledge-based society in which all men, women and children are capable of utilizing available potentials and opportunities to contribute to development.

# 5.0 GOAL / MISSION STATEMENT

# The District Assembly exists to facilitate improvement in the quality of life of the people within the Assembly’s jurisdiction through equitable provision of services for the total development of the district, within the context of Good Governance.

# 6.0 CORE FUNCTIONS OF THE ASSEMBLY

The Awutu Senya District Assembly by Law, constitutes the highest Political and Administrative Authority in the District (Local Governance Act, 2016, Act 936).

The District Assembly is charged with three (3) Statutory Functions, namely: Deliberative, Legislative and Executive functions. By this, it

- Ensures the overall development of its territorial jurisdiction.

- Promotes and supports productive activities and socio-economic development.

- Initiates programmes for the development of basic infrastructure.

- It is also charged with the task of programme formulation as well as the execution of plans, programmes     and strategies for the efficient mobilization of the resources necessary for the overall development of the Municipality.

- It is also responsible for the enactment of Bye-Laws and the preparation of budget estimates.

- The Assembly also coordinates, integrates and harmonizes the execution of programmes and projects under the approved budget.

- The District Assembly in the performance of its functions, is subject to the general guidance and direction of the President on matters of national policy, and shall act in co-operation with the appropriate public corporation, statutory body or non-governmental organizations.

# 7.0 FINANCIAL PERFORMANCE

## 7.1 FINANCIAL PERFORMANCE - REVENUE

Table 1a: Revenue Performance- All Revenue Sources

| REVENUE PERFORMANCE - ALL REVENUE SOURCES |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Revenue Item | 2018 |  | 2019 |  | 2020 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at Aug. 2020 | % performance as at Aug., 2020 |
| IGF | 635,260.00 | 621,471.11 | 700,325.00 | 680,663.34 | 831,415.00 | 463,646.19 | 55.77 |
| Compensation Transfer | 1,794,720.29 | 2,337,230.82 | 2,227,298.90 | 2,673,716.62 | 2,324,028.00 | 2,372,883.87 | 102.10 |
| Goods & Services Transfer | 52,518.41 | 78,064.23 | 76,603.07 | 57,081.71 | 97,171.40 | 65,451.02 | 67.36 |
| Assets Transfer | - | - | - | - | - | - | - |
| DACF | 3,859,951.00 | 1,745,634.77 | 4,417,283.03 | 2,197,057.52 | 4,525,050.42 | 1343832.88 | 29.70 |
| DDF/DACF-RFG | 612,475.00 | 489,938.00 | 1,051,000.00 | 839,091.19 | 692,232.53 | 168,480.31 | 24.34 |
| UDG | - | - | - | - | - | - | - |
| Other Transfer: |  |  |  |  |  |  |  |
| CIDA/MAG | 66,592.76 | 69,791.13 | 153,665.65 | 153,765.65 | 153,665.65 | 105,286.24 | 68.52 |
| Japan Embassy | - | - | 600,000.00 | - | 600,000.00 | - | - |
| World Bank (GPSNP) | - | - | - | - | 2,000,000.00 | 30,000.00 | 1.50 |
| Total | 7,021,517.46 | 5,342,130.06 | 9,226,175.65 | 6,601,376.03 | 11,223,563.00 | 4,549,580.51 | 40.54 |

Table 1b: Revenue Performance - IGF ONLY

| REVENUE PERFORMANCE- IGF ONLY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Revenue Item | 2018 |  | 2019 |  | 2020 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at Aug. 2020 | % performance as at Aug., 2020 |
| Rate | 103,670.00 | 78,132.82 | 60,910.00 | 55,114.62 | 134,000.00 | 22,649.32 | 16.90 |
| Fees | 145,595.00 | 120,041.50 | 229,045.00 | 235,789.10 | 238,745.00 | 124,576.00 | 52.18 |
| Fines | - | - | - | - | - | 253.00 | 100.00 |
| Licenses | 180,175.00 | 134,986.80 | 197,770.00 | 171,144.00 | 211,770.00 | 120,687.00 | 56.99 |
| Lands | 176,200.00 | 210,408.75 | 198,900.00 | 200,664.40 | 200,500.00 | 188,906.24 | 94.22 |
| Rent | 27,120.00 | 5,884.80 | 13,200.00 | 17,951.22 | 45,400.00 | 4,262.00 | 9.39 |
| Investment | - | - | - | - | - | - |  |
| Miscellaneous | 2,500.00 | - | 500.00 | - | 1,000.00 | 2,312.63 | 231.26 |
| Total | 635,260.00 | 549,454.67 | 700,325.00 | 680,663.34 | 831,415.00 | 463,646.19 | 55.77 |

Figure 1: 2020 REVENUE PERFORMANCE-IGF ONLY

## 7.2 FINANCIAL PERFORMANCE-EXPENDITURE

Table 2a: Expenditure Performance- All Department GOG Only

| EXPENDITURE PERFORMANCE (ALL DEPARTMENT) - GOG ONLY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expenditure Item | 2018 |  | 2019 |  | 2020 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at Aug., 2020 | % Performance as at Aug. 2020 |
| Compensation | 1,794,730.29 | 2,337,230.82 | 2,227,298.90 | 2,673,716.62 | 2,324,028.00 | 2,372,883.87 | 102.10 |
| Goods & Services | 52,508.41 | 78,064.23 | 76,603.07 | 57,081.71 | 97,171.40 | 65,451.02 | 67.36 |
| Assets | - | - | - | - | - | - | - |
| Total | 1,847,238.70 | 2,415,295.05 | 2,303,901.97 | 2,730,798.33 | 2,421,199.40 | 2,438,334.89 | 100.71 |

Table 2b: Expenditure Performance (All Department) - IGF Only

| EXPENDITURE PERFORMANCE (ALL DEPARTMENT) - IGF ONLY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expenditure Item | 2018 |  | 2019 |  | 2020 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at Aug. 2020 | %Performance as at Aug. 2020 |
| Compensation | 109,447.74 | 74,879.59 | 105,317.62 | 130,471.09 | 105,159.00 | 81,110.51 | 80.98 |
| Goods & Services | 398,760.26 | 251,942.10 | 454,942.38 | 621,793.76 | 561,213.00 | 330,348.05 | 58.86 |
| Assets | 127,052.00 | - | 140,065.00 | 46,441.53 | 170,043.00 | 29,707.85 | 17.47 |
| Total | 635,260.00 | 326,821.69 | 700,325.00 | 798,706.38 | 831,415.00 | 442,038.13 | 53.06 |

Figure 2: 2020 EXPENDITURE PERFORMANCE-IGF ONLY

Table 2c: Expenditure Performance- All Sources

| Expenditure Item | 2018 |  | 2019 |  | 2020 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at Aug. | % age Performance as at Aug. 2020 |
| Compensation | 1,904,178.03 | 2,485,688.59 | 2,377,616.65 | 2,804,157.71 | 2,424,187.00 | 2,453,994.38 | 101.23 |
| Goods and Services | 1,914,573.43 | 1,568,473.81 | 2,762,800.00 | 1,775,219.77 | 3,004,008.00 | 1,160,281.21 | 38.62 |
| Assets | 3,202,766.00 | 1,614,686.07 | 4,085,759.00 | 1,535,523.79 | 5,795,368.00 | 606,078.82 | 10.46 |
| Total | 7,021,517.46 | 5,668,848.47 | 9,226,175.65 | 6,114,901.27 | 11,223,563.00 | 4,220,354.41 | 37.60 |

# Figure 3: 2020 EXPENDITURE PERFORMANCE-ALL FUNDING SOURCES

# 8.0 NON FINANCIAL PERFORMANCE BY PROGRAMME

## 8.1 KEY ACHIEVEMENTS (2020)

Key achievement of the Awutu Senya District Assembly for the period 1st January, 2020 to August 2020 are as follows:

- Completed 1No. 3-Unit Teachers Quarters at Krobonshie

- Constructed 1No. 3-Unit classroom block at Ofaaso

- Constructed 2No. 0.90m Diameter Single Cell Pipe Culvert width 8m and approaching filling at Kofi Ansah and Oframase

- Constructed 1No. Concrete foot bridge at Bawjiase Zongo

- Constructed  Ofadaa CHPS

- Constructed pipe water supply system for saline belt Communities( Bontrase and Papaase clusters

- Construction of 5No. System Management Office ( i.e Management of the Pipe water system)

Figure 4: 1No. 3-Unit Teachers Quarters at Krobonshie

Figure 5: 1No. 3-Unit classroom block at Ofaaso

Figure 6: 1No. Footbridge at Bawjiase Zongo

## 8.2 POLICY OUTCOME INDICATORS AND TARGETS

Table 3a: Policy Outcome Indicators and Targets

| Outcome Indicator Description | Unit of Measurement | Baseline |  | Actual Performance |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Year 2019 | Value | Target For the Year 2020 | Actuals as at Aug. |
| Improved Revenue Mobilization and management | % growth in IGF generated | 2019 | 23.88 | 22.15 | -37.50 |
| Increase access to safe and potable water | Proportion of population with access to safe water | 2019 | 65 | 80 | 73 |
| Improved Road network within the District | Length (km) of Feeder Roads maintained /rehabilitated | 2019 | 30km | 50km | 30km |
| Improved Human Settlement and Housing | Increase number of communities with their lands well planned/schemed. | 2019 | 2 | 2 | 0 |
| Increase inclusive and equitable access to education at all levels | Number of Education Facilities Constructed | 2019 | 0 | 4 | 4 |
| Improved access to quality healthcare | Number of health facilities Constructed | 2019 | 1 | 4 | 0 |
| Improved agricultural productivity | Ratio of Extension Officer to farmer | 2019 | 1:3000 | 1:1000 | 1:2800 |
| Improved Private sector Development | Number of Entrepreneurs and SMEs trained/ supported | 2019 | 130 | 200 | 90 |
| Improved Environmental Sanitation | Number of sanitation facilities constructed | 2019 | 3 | 3 | 0 |

## 8.3 KEY PERFORMANCE INFORMATION FOR BUDGET PROGRAMMES

Table 3b: Key Performance Information for Budget Programmes

| Management and Administration |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key/Main Outputs | Output Indicator | Past Years |  |  |  |
|  |  | 2019 Target | 2019 Actual | 2020 Target | 2020 Actual as at Aug. |
| Land for Assembly Projects Acquired and documented | Number of acres acquired | 50 acres | 50 acres | 50 acres | 0 |
| DPCU monitoring & evaluation conducted | Number of report on monitoring | 4 | 4 | 4 | 0 |
| Area Council offices Constructed | Number of Area Council offices constructed | 4 | 0 | 1 | 0 |
| Infrastructure Delivery and Management |  |  |  |  |  |
| Town Street Named and Properties Addressed | Number of towns streets named and properties addressed | 4 | 2 | 2 | 0 |
| Reshaping, spot improvement and construction roads | 50km of roads reshaped, spot improved and constructed | 35km | 35km | 50km | 30km |
| Construction and repair of broken down boreholes | Number of broken down boreholes repaired constructed | 5 No. repairs | 0 | 5 to be repair, 2 to be con structed | 0 |
| Social Services Delivery |  |  |  |  |  |
| Bursaries and Scholarships for Brilliant but needy student | Number of Students supported | 500 | 140 | 500 | 85 |
| Education facilities Constructed | Number of Education facilities Constructed | 4 | 0 | 4 | 4 |
| Health facilities constructed | Number of health facilities constructed/ Rehabilitated | 4 | 0 | 4 | 1 |

| Economic Development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key/Main Outputs | Output Indicator | Past Years |  |  |  |
|  |  | 2019 Target | 2019 Actual | 2020 Target | 2020 Actual as at Aug. |
| Markets Constructed | Number of markets constructed | 3 | 0 | 3 | 1 |
| Potential and Existing Entrepreneurs/ SMEs trained in various economic ventures | Number of beneficiaries trained | 150 | 130 | 250 | 90 |
| Coconut plantation for PERD increased | Number of coconut seedlings Procured and distributed | 11,000 | 11,000 | 4,000 | 0 |
| Environmental and Sanitation Management |  |  |  |  |  |
| Disaster Management Campaigns conducted | Number of Community gatherings held | 12 | 10 | 12 | 4 |

## 8.4 2020 BUDGET PROGRAMME PERFORMANCE

Table 3c: 2020 Budget Programme Performance

| Budget Programme | Budget | Actual as at Aug. 2020 |
| --- | --- | --- |
| Management and Administration | 5,928,182.87 | 2,602,862.67 |
| Infrastructure Delivery and Management | 1,265,925.36 | 208,356.96 |
| Social Services Delivery | 2,544,461.55 | 981,562.31 |
| Economic Development | 649,515.37 | 216,865.53 |
| Environmental Management | 835,477.85 | 210,706.94 |
| Total | 11,223,563.00 | 4,220,354.41 |

# 9.0 FINANCIALS

## 9.1 2020 KEY PROJECTS AND PROGRAMMES FROM ALL SOURCES

Table 4a: 2020 Key Projects and Programmes from All Sources

| No. | Names of Project | Amount budgeted | Actual payment as at Aug. 2020 | Outstanding payment |
| --- | --- | --- | --- | --- |
|  | Construction of NHIS offices at Awutu Beraku | 186,185.23 | 69,670.90 | 116,514.33 |
| 1 | Construction of 1No. 3-bedroom Residential accommodation at Awutu Beraku( ad’tional wk incl’sve) | 342,321.61 | 161,594.55 | 180,727.06 |
| 2 | Completion of Lorry Park (Lower) at Bawjiase Market | 498,611.63 | 473,417.49 | 25,194.14 |
| 3 | Construction of concrete foot bridge at Bawjiase Zongo | 125,706.90 | 115,960.00 | 9,746.90 |
|  | Completion of Jei-Krodua Area Council | 77,570.22 | 69,740.73 | 7,829.49 |
| 4 | Rehabilitation of D/A JHS at Ofaaso | 138,273.78 | 131,352.17 | 6,921.61 |
| 5 | Construction of 3-storey office complex and Assembly Hall at Awutu Beraku | 1,202,596.81 | 1,000,466.39 | 202,130.42 |
| 6 | Completion of Teachers Quarters at Krobonshie | 188,133.00 | 169,346.53 | 18,786.47 |
| 8 | Construction of market store at Bawjiase | 304,006.75 | 124,143.48 | 179,863.27 |
| 9 | Construction of 2No. 0.90m Diameter Single Cell Pipe Culvert width 8m and approaching filling at Kofi Ansah and Oframase | 82,893.24 | 78,685.66 | 4,207.58 |
| 10 | Completion of CHPS Compound at Bonsueku | 154,424.66 | 57,341.80 | 97,082.86 |
| 12 | Completion of 1No. 32-Seater W/C Public Toilet at Awutu Beraku | 143,124.98 | - | 143,124.98 |
| 13 | Completion of 1No. 12-Seater W/C Public Toilet at Bonsuoku | 78,259.63 | - | 78,259.63 |
| 14 | Completion of Durbar Ground/Mini- Market at Bebianiha | 72,093.31 | - | 72,093.31 |
| 16 | Extension and supply of electricity to CHPS compound at Ofadaa | 173,548.16 | 156,033.83 | 17,514.33 |
| 17 | Const. of 1No. 4-unit classroom block with ancillary facility at Bawjiase | 274,580.25 | 162,861.65 | 111,718.60 |

## 9.2 SANITATION BUDGET PERFORMANCE

Table 4b: Sanitation Budget Performance

| Liquid Waste |  |  |  |
| --- | --- | --- | --- |
| No. | Names of Activity/Project | Budget | Actual as at Aug., 20 |
| 1 | Organise Training for WATSAN committee members | 9,000.00 | 8,000.00 |
| 2 | Intensify house to house inspection to reduce cholera outbreak. | 1,500.00 | 2,000.00 |
| 3 | Construction of 1No. 32-seater WC Toilet at Awutu Beraku | 143,124.98 | - |
| 4 | Construction of 1 No. 12 seater WC Toilet at Bonsuako | 78,259.63 | - |
| 5 | Construction of Culverts at Kofi Ansah, Oframase and Obrachire | 82,893.24 | 78,685.66 |
| 6 | Construction of Toilet and completion of RCH centre at Bontrase Health centre | 20,000.00 | - |
| 8 | Support and expand the CLTS program in the District | 5,000.00 | 2,000.00 |
| Solid Waste |  |  |  |
| No. | Names of Activity/Project | Budget | Actual as at Aug., 20 |
| 1 | Acquisition of land for final disposal sites. | 40,000.00 | - |
| 2 | Provide Uniform materials & ID cards for field staff and acquisition of Sanitary tools & Disinfectant | 8,500.00 | - |
| 3 | Clearing of existing heaps of refuse sites and work on final refuse disposal site | 30,000.00 | 15,000.00 |
| 4 | Purchase of 3 No. Motorbikes | 12,000.00 |  |
| 5 | Organise National/District clean-up exercise on National Sanitation Days and other waste management activities | 20,000.00 | 10,000.00 |
| 6 | Rehabilitate one (1) slaughter slab | 10,000.00 | - |
| 7 | Fumigation Sanitation Improvement Package | 331,200.00 | 95,021.28 |
| 8 | Acquisition of 2No. Communal refuse containers | 15,000.00 | - |
| 9 | Support waste management activities (All area councils) | 24,000.00 | - |

## 9.3 GOVERNMENT FLAGSHIP PROJECTS/PROGRAMMES

## (Assembly’s Contribution)

Table 4c: Government Flagship Projects/Programmes

| No | Name of Activity/Project | Budget | Actual as at August, 2020 |
| --- | --- | --- | --- |
| 1 | Support Planting and Rearing for Food and Jobs | 10,000.00 | 4,000.00 |
| 2 | Support Planting for Export and Rural Development [PERD] | 30,000.00 | - |

# OUTLOOK FOR 2021-2024

# 10.0 POLICY OBJECTIVES FOR 2021

Table 5: District Adopted Policy Objectives For 2021

| FOCUS AREA | POLICY OBJECTIVES | BUDGET ALLOCATION |
| --- | --- | --- |
| Local Government and Decentralisation | Deepen political and administrative Decentralisation | 3,914,614.71 |
| Strong and Resilient Economy | Ensure Improved Fiscal Performance and Sustainability | 54,500.00 |
| Education and Training | Enhance inclusive and equitable access to, and participation in quality education at all levels | 1,169,005.53 |
| Health Delivery | Ensure affordable, equitable and easily accessible health care services | 2,115,427.54 |
| Social Protection | Strengthen Social Protection, especially for children, women, persons with disability and the elderly | 528,161.90 |
| Agricultural and Rural Development | Promote demand –driven approach to agricultural development | 1,558,282.06 |
| Human Settlement and Housing | Promote sustainable spatially integrated balanced and orderly development of human settlement | 1,780,924.15 |
| Private sector development | Support entrepreneurs and SME development | 793,119.88 |
| Disaster Management | Promote proactive planning for disaster prevention and mitigation | 31,418.72 |
| Deforestation, desertification and soil erosion | Combat Deforestation, desertification and soil erosion | 25,000.00 |
| Total |  | 11,970,454.49 |

# 11.0 POLICY OUTCOME INDICATORS AND TARGETS

Table 6: Policy Outcome Indicators and Targets

| Outcome Indicator Description | Unit of Measurement | Baseline |  | Latest status |  | Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Year 2019 | Value | Year 2020 | Value | Year 2021-2024 | Value |
| Improved Revenue Mobilization and management | % growth in IGF generated | 2019 | 23.88% | 2020 | -37.5% | 2021 | 10% |
| Improved local governance service delivery | % score of DPAT Performance | 2019 | 96 | 2020 | not yet | 2021 | 100 |
| Increased inclusive and equitable access to education at all levels | Number of school infrastructure constructed | 2019 | 0 | 2020 | 4 | 2021 | 5 |
|  | % pass in BECE | 2019 | 74 | 2020 | 66 | 2021 | 80 |
|  | Number of needy but brilliant students enrolment | 2019 | 140 | 2020 | 85 | 2021 | 200 |
| Improved access to quality healthcare | Number of health facilities Constructed/ Rehabilitated | 2019 | 0 | 2020 | 4 | 2021 | 4 |
| Improved Agricultural Productivity | Number of farmers trained and supported | 2019 | 4,000.00 | 2020 | 5,000.00 | 2021 | 5000 |
|  | Number of demonstration farms established | 2019 | 7 | 2020 | 5 | 2021 | 7 |
| Increase access to safe and potable water | % of population provided with potable water | 2019 | 65% | 2020 | 73% | 2021 | 80% |
| Improve Road netwok | Number of Communities with access to good road | 2019 | 30km | 2020 | 30km | 2021 | 60km |

| Outcome Indicator Description | Unit of Measurement | Baseline |  | Latest status |  | Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Year 2019 | Value | Year 2020 | Value | Year 2021-2024 | Value |
| Improved Social Protection | Number of PWDs supported | 2019 | 61 | 2020 | 3 | 2021 | 60 |
|  | Number of Women and Vulnerable groups supported | 2019 | 271 | 2020 | 290 | 2021 | 290 |
| Private sector Development Promoted | Number of Entrepreneurs and SMEs supported | 2019 | 40 | 2020 | 45 | 2021 | 50 |
|  | Number of Markets constructed | 2019 | 3 | 2020 | 0 | 2021 | 3 |
| Improved Environmental Sanitation | Number of disaster community gatherings held | 2019 | 15 | 2020 | 4 | 2021 | 15 |
|  | Number of Trees planted | 2019 | 200 | 2020 | 0 | 2021 | 200 |

# 12.0 2021-2024 REVENUE PROJECTIONS

## 12.1 2021-2024 REVENUE PROJECTIONS – IGF ONLY

Table 7a: 2021-2024 Revenue Projections – IGF Only

| 2021-2024 REVENUE PROJECTIONS – IGF ONLY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Revenue Item | 2020 |  | 2021 | 2022 | 2023 | 2024 |
|  | Budget | Actual as at Aug. 2020 | Projection | Projection | Projection | Projection |
| Rate | 134,000.00 | 22,649.32 | 86,000.00 | 94,600.00 | 104,060.00 | 114,466.00 |
| Fees | 238,745.00 | 124,576.00 | 246,365.46 | 271,002.01 | 298,102.21 | 327,912.43 |
| Fines | - | 253.00 | 5,000.00 | 5,500.00 | 6,050.00 | 6,655.00 |
| Licenses | 211,770.00 | 120,687.00 | 228,890.10 | 251,779.11 | 276,957.02 | 304,652.72 |
| Lands | 200,500.00 | 188,906.24 | 247,449.63 | 272,194.59 | 299,414.05 | 329,355.46 |
| Rent | 45,400.00 | 4,262.00 | 33,746.34 | 37,120.97 | 40,833.07 | 44,916.38 |
| Investment | - | - |  | - | - | - |
| Miscellaneous | 1,000.00 | 2,312.63 | 3,500.00 | 3,850.00 | 4,235.00 | 4,658.50 |
| Total | 831,415.00 | 463,646.19 | 850,951.53 | 936,046.68 | 1,029,651.35 | 1,132,616.49 |

Figure 7: 2021 REVENUE PROJECTION-IGF ONLY

12.2 REVENUE PROJECTION- ALL REVENUE SOURCES

Table 7b: Revenue Projection- All Revenue Sources

| REVENUE PROJECTION- ALL REVENUE SOURCES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | 2020 |  | 2021 | 2022 | 2023 | 2024 |
|  | Budget | Actual as at Aug., 2020 | PROJECTION | PROJECTION | PROJECTION | PROJECTION |
| IGF | 831,415.00 | 463,646.19 | 850,951.42 | 936,046.56 | 1,029,651.22 | 1,132,616.34 |
| Compensation Transfer | 2,324,028.00 | 2,372,883.87 | 3,034,945.27 | 3,338,439.80 | 3,672,283.78 | 4,039,512.15 |
| Goods & Services Transfer | 97,171.40 | 65,451.02 | 90,527.00 | 99,579.70 | 109,537.67 | 120,491.44 |
| Assets Transfer | - | - |  | - | - | - |
| DACF-Assembly | 4,525,050.42 | 1,343,832.88 | 4,075,050.80 | 4,482,555.88 | 4,930,811.47 | 5,423,892.61 |
| DACF-MP |  |  | 450,000.00 | 495,000.00 | 544,500.00 | 598,950.00 |
| DACF-RFG (Investment) | 692,232.53 | 168,480.31 | 1,700,216.00 | 1,870,237.60 | 2,057,261.36 | 2,262,987.50 |
| DACF-RFG (Capacity Building) |  |  | 45,859.00 | 50,444.90 | 55,489.39 | 61,038.33 |
| DP Support: |  |  |  |  |  |  |
| CIDA (MAG) | 153,665.65 | 105286.24 | 115,210.00 | 126,731.00 | 139,404.10 | 153,344.51 |
| Other Transfers: |  |  |  |  |  |  |
| World Bank ( GPSNP) | 2,000,000.00 | 30,000.00 | 1,336,895.00 | 1,336,895.00 | 1,336,895.00 | 1,336,895.00 |
| IDA | 600,000.00 | - | - | - | - | - |
| Rural Enterprise Programme | - | - | 270,800.00 | 270,800.00 | 270,800.00 | 270,800.00 |
| Total | 11,223,563.00 | 4,549,580.51 | 11,970,454.49 | 13,006,730.44 | 14,146,633.98 | 15,400,527.88 |

# 13.0 EXPENDITURE BY BUDGET PROGRAMME AND ECONOMIC CLASSIFICATION -ALL FUNDING SOURCES

Table 8: Expenditure by Budget Programme and Economic Classification

| BUDGET PROGRAMME | COMPENSATION OF EMPLOYEES | AMOUNT GH¢ |  |  |
| --- | --- | --- | --- | --- |
|  |  | GOODS & SERVICE | CAPITAL EXPENDITURE | TOTAL |
| MANAGEMENT AND ADMINISTRATION | 2,086,287.27 | 1,383,140.47 | 499,686.97 | 3,969,114.71 |
| INFRASTRUCTURE DELIVERY AND MANAGEMENT | 282,548.04 | 131,704.16 | 1,366,671.95 | 1,780,924.15 |
| SOCIAL SERVICES DELIVERY | 379,674.90 | 1,203,417.48 | 2,229,502.59 | 3,812,594.97 |
| ECONOMIC DEVELOPMENT | 480,931.02 | 1,099,869.76 | 770,601.16 | 2,351,401.94 |
| ENVIRONMENTAL AND SANITATION MANAGEMENT | - | 56,418.72 | - | 56,418.72 |

# 14.0 KEY PERFORMANCE INFORMATION FOR BUDGET PROGRAMMES

Table 9: Key Performance Information for Budget Programmes

| Management and Administration |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key/Main Outputs | Output Indicator | Past Years |  |  |  | Projections |  |  |  |
|  |  | 2019 Target | 2019 Actual | 2020 Target | 2020 Actual as at Aug | Budget Year | Indicative Year | Indicative Year | Indicative Year |
|  |  |  |  |  |  | 2021 | 2022 | 2023 | 2024 |
| Administrative Meetings Held | Number of Administrative meetings held | 4 | 3 | 4 | 2 | 4 | 4 | 4 | 4 |
| 350 acres of Land Acquired and documented for Assembly Projects | Signed Indenture/ Land title | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 |
| Town Hall/ Stakeholders meetings Organised | Number of Town hall meetings organised | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 4 |
| Infrastructure Development and Management |  |  |  |  |  |  |  |  |  |
| Town Streets named and properties addressed | Number of streets sinages mounted |  |  |  |  |  |  |  |  |
| Deplorable Feeder Roads Reshaped | Length (Km) of Feeder roads reshaped | 35km | 35km | 50km | 30km | 60km | 60km | 60km | 60km |
| Statutory Planning meetings convened | Number of Meetings Organized | 4 |  | 4 | 1 | 4 | 4 | 4 | 4 |
| Social Services Delivery |  |  |  |  |  |  |  |  |  |
| Brilliant but Needy students Supported | Number of needy students supported | 500 | 140 | 500 | 85 | 150 | 150 | 150 | 150 |
| Education facilities Constructed | Number of Education facilities Constructed | 4 | 0 | 4 | 4 | 3 | 4 | 4 | 4 |

| Key/Main Outputs | Output Indicator | Past Years |  |  |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 Target | 2019 Actual | 2020 Target | 2020 Actual as at Aug | Budget Year | Indicative Year | Indicative Year | Indicative Year |
|  |  |  |  |  |  | 2021 | 2022 | 2023 | 2024 |
| Health facilities constructed | Number of health facilities constructed/ Rehabilitated | 4 | 0 | 4 | 1 | 3 | 3 | 3 | 3 |
| Final Disposal Site Properly maintained | Number of fumigation/ Disinfection Exercise carried out | 12 | 4 | 12 | 2 | 12 | 12 | 12 | 12 |
| Economic Development |  |  |  |  |  |  |  |  |  |
| Market facilities Constructed | Number of markets constructed | 3 | 0 | 3 | 1 | 2 | 2 | 2 | 3 |
| Potential and Existing Entrepreneurs/ SMEs trained in various economic ventures | Number of beneficiaries trained | 150 | 130 | 250 | 90 | 200 | 200 | 200 | 200 |
| Coconut plantation for PERD increased | Number of coconut seedlings Procured and distributed | 11,000 | 11,000 | 4000 | 0 | 4000 | 5000 | 6000 | 6000 |
| Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |
| Staff Capacity Built on environmental management | Number of trainer of trainees workshops held | 4 | 2 | 4 | 1 | 4 | 4 | 4 | 4 |
| Public Education to manage and mitigate disaster Conducted | Number of community gatherings held | 12 | 10 | 12 | 4 | 12 | 12 | 12 | 12 |
| Trees Planted in Public Schools within the District | Number of trees planted | 200 | 0 | 200 | 0 | 200 | 200 | 200 | 200 |

# 15.0 2021 EXPENDITURE BY BUDGET PROGRAMME, PROJECTS AND ECONOMIC CLASSIFICATION

Table 10: 2021 Expenditure by Budget Programme, Projects and Economic Classification

| BUDGET PROGRAMME | KEY PRIORITY PROJECT FOR 2021 | AMOUNT GHC |  |  |
| --- | --- | --- | --- | --- |
|  |  | GOODS & SERVICE | CAPITAL INVESTMENT | TOTAL |
| MANAGEMENT & ADMINSTRATION | Acquisition and Documentation of Land for Assembly Projects |  | 30,000.00 | 30,000.00 |
|  | Completion of Jei-Krodua Area Council Office |  | 7,829.49 | 7,829.49 |
|  | Construction of 3-Story Office Accommodation with Assembly Hall (Phase II) |  | 202,130.42 | 202,130.42 |
|  | Construction of 3-Bedroom Residencial Accommodation |  | 180,727.06 | 180,727.06 |
| INFRASTRUCTURE DELIVERY AND MANAGEMENT | Rehabilitation of Pobikwa-Annan Feeder road(4.9km) |  | 500,000.00 | 500,000.00 |
|  | Dredging and Construction of 1No. Footbridge at Ponpong |  | 180,000.00 | 180,000.00 |
|  | Construction of 5No. culverts at Obrachire ( 2), Bawjiase, Ankwando and Akrapa |  | 207,233.10 | 207,233.10 |
|  | Extension of Ghana Water Company water pipelines at Awutu Beraku |  | 203,958.93 | 203,958.93 |
|  | Construction 2No. Boreholes at Mbofrakrom and Obaakoasem |  | 55,479.92 | 55,479.92 |
| SOCIAL SERVICES DELIVERY | Renovation of 1no. 3unit classroom block at Akpetashie Nkwanta JHS ( MP) |  | 34,076.70 | 34,076.70 |
|  | Construction of 1No.4 unit classroom block with ancillary facilities at Bawjiase D/A |  | 111,718.60 | 111,718.60 |
|  | Construction of 1No. 3unit Classroom Block with ancillary facilities at Senya DA |  | 480,810.55 | 480,810.55 |

| BUDGET PROGRAMME | KEY PRIORITY PROJECT | AMOUNT GHC |  |  |
| --- | --- | --- | --- | --- |
|  |  | GOODS & SERVICE | CAPITAL INVESTMENT | TOTAL |
|  | Renovation of Staff Quarters, Bontrase Health Centre |  | 69,412.30 | 69,412.30 |
|  | Construction of 1No. Semi-detached Nurses quarters at Awutu Beraku |  | 384,000.00 | 384,000.00 |
|  | Construction of Toilet and completion of Reproductive Child Health Center at Bontrase Health Centre (MP) |  | 22,000.00 | 22,000.00 |
|  | Construction of NHIS offices at Awutu Beraku |  | 116,514.33 | 116,514.33 |
|  | Rehabilitation of CHPS Compound at Mayenda, Akrabong, Tawaikwa and Okwampa |  | 227,770.13 | 227,770.13 |
|  | Acquisition of Land for Final Waste Disposal at Senya Beraku |  | 40,000.00 | 40,000.00 |
|  | Construction of 1No. 32 Seater w/c at Awutu Beraku, 1No 12 seater w/c at Bonsueku |  | 143,124.98 | 143,124.98 |
|  | Construction of 1No 12 seater w/c at Bonsueku |  | 78,259.63 | 78,259.63 |
| ECONOMIC DEVELOPMENT | Construction of 3No. Market Shed at Awutu Beraku |  | 42,498.87 | 42,498.87 |
|  | Construction of Office Accommodation for the Didtrict Business Advisory Centre (BAC) |  | 324,475.95 | 324,475.95 |
|  | Construction of 2No. Shed for Cassva Mill at Bontrase and Saakwa |  | 53,967.10 | 53,967.10 |
|  | Construction of mini Market / Durbar grand at Bibianiha |  | 72,093.31 | 72,093.31 |

16.0 GOVERNMENT FLAGSHIP PROJECTS/PROGRAMMES FOR 2021 (ASSEMBLY SUPPORT)

Table 11: Government Flagship Projects/Programmes For 2021

| NO | Name of Activity/Project | Budget | Funding Source |
| --- | --- | --- | --- |
| 1 | Procurement and Distribution of 4,000 coconut seedlings [Planting for Export & Rural Development (PERD)] | 40,000.00 | DACF |
| 2 | Monitoring of Planting and Rearing for Food and Jobs | 10,000.00 | DACF |

# 17.0 2021-2024 EXPENDITURE PROJECTIONS BY ECONOMIC CLASSIFICATION- ALL FUNDING SOURCES

Table 12: 2021-2024 Expenditure Projections by Economic Classification- all funding sources

| EXPENDITURE ITEM | 2020 BUDGET | ACTUAL AS AT AUG. 2020 | 2021 | 2022 | 2023 | 2024 |
| --- | --- | --- | --- | --- | --- | --- |
| COMPENSATION | 2,424,187.00 | 2,453,994.38 | 3,229,441.23 | 3,552,385.35 | 3,907,623.89 | 4,298,386.28 |
| GOODS AND SERVICES | 3,004,008.00 | 1,160,281.21 | 3,874,550.59 | 4,262,005.65 | 4,688,206.21 | 5,157,026.84 |
| ASSET | 5,795,368.00 | 606,078.82 | 4,866,462.67 | 5,353,108.94 | 5,888,419.83 | 6,477,261.81 |
| TOTAL | 11,223,563.00 | 4,220,354.41 | 11,970,454.49 | 13,167,499.94 | 14,484,249.93 | 15,932,674.93 |

# 18.0 SUMMARY OF EXPENDITURE BUDGET BY DEPARTMENT, ITEM AND FUNDING SOURCES-2021

Table 12: Summary of Expenditure Budget by Department, Item and Funding Sources-2021

| Department | Compensation | Goods and services | Assets | Total | Funding (indicate amount against the funding source) |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IGF | GOG | DACF | DACF-RFG | OTHERS |  |
| Central Administration | 2,086,287.27 | 1,328,640.47 | 499,686.97 | 3,914,614.71 | 500,897.72 | 1,904,665.31 | 1,463,192.68 | 45,859.00 | - | 3,914,614.71 |
| Works department | 208,456.20 | 25,208.08 | 1,326,671.95 | 1,560,336.23 | 9,628.08 | 224,036.20 | 285,479.92 | 541,192.03 | 500,000.00 | 1,560,336.23 |
| Department of Agriculture | 480,931.02 | 1,065,451.04 | 11,900.00 | 1,558,282.06 | 4,814.04 | 517,363.02 | 84,000.00 | - | 952,105.00 | 1,558,282.06 |
| Department of Social Welfare &Community Development | 379,674.90 | 148,487.00 | - | 528,161.90 | 6,023.20 | 393,447.90 | 128,690.80 | - | - | 528,161.90 |
| Schedule 2 |  |  |  |  |  |  |  |  |  |  |
| Physical Planning | 74,091.84 | 106,496.08 | 40,000.00 | 220,587.92 | 9,628.08 | 85,959.84 | 125,000.00 | - | - | 220,587.92 |
| Trade and Industry | - | 34,418.72 | 758,701.16 | 793,119.88 | 60,094.67 | - | 100,093.31 | 362,131.90 | 270,800.00 | 793,119.88 |
| Finance | - | 54,500.00 | - | 54,500.00 | 37,000.00 | - | 17,500.00 | - | - | 54,500.00 |
| Education youth and sports | - | 168,418.72 | 1,000,586.81 | 1,169,005.53 | 6,418.72 | - | 953,897.95 | 208,688.86 | - | 1,169,005.53 |
| Disaster Prevention and Management | - | 31,418.72 | - | 31,418.72 | 6,418.72 | - | 25,000.00 | - | - | 31,418.72 |
| Natural resource conservation | - | 25,000.00 | - | 25,000.00 | - | - | 25,000.00 | - | - | 25,000.00 |
| Health | - | 886,511.76 | 1,228,915.78 | 2,115,427.54 | 210,028.19 | - | 1,317,196.14 | 588,203.21 | - | 2,115,427.54 |
| TOTALS | 3,229,441.23 | 3,874,550.59 | 4,866,462.67 | 11,970,454.49 | 850,951.42 | 3,125,472.27 | 4,525,050.80 | 1,746,075.00 | 1,722,905.00 | 11,970,454.49 |

# 19.0 PROJECTS AND PROGRAMS FOR 2021 AND CORRESPONDING COST AND JUSTIFICATION

Table 13: Projects and Programs for 2021 and Corresponding Cost and Justification

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | MANAGEMENT AND ADMINISTRATION |  |  |  |  |  |  |  |
| i | General Administration |  |  |  |  |  |  |  |
| 1 | Compensation of employees (All Department) | 110,135.96 | 2,976,646.87 |  |  |  | 3,086,782.83 | To remunerate Employees for effective local governance and decentralisation |
| 2 | Other Compensation related Allowances | 84,360.00 | 58,298.40 |  |  |  | 142,658.40 | To remunerate Employees for effective local governance and decentralisation |
| 3 | Support to Traditional Authorities | 4,000.00 |  | 22,000.00 |  |  | 26,000.00 | To Secure landed properties of the Assembly for effective local governance and decentralisation |
| 4 | Procure Building Materials to support Community Initiated Project/ Counterpart Funding |  |  | 30,000.00 |  |  | 30,000.00 | To procure materials to support CIP to facilitate development and decentralisation |
| 5 | Training of Assembly Members & Unit Committee Members |  |  | 34,127.20 |  |  | 34,127.20 | Ensure the functionality of zonal councils for effective local governance and decentralisation |
| 6 | Procure Logistics & Supports to Sub-Structures |  |  | 37,170.51 |  |  | 37,170.51 | Ensure the functionality of zonal councils for effective local governance and decentralisation |
| 7 | Completion of Jei-Krodua Area Council Office |  |  | 7,829.49 |  |  | 7,829.49 | Provide office space for the sub-structure for effective local governance and decentralisation |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | Procurement of Office Materials and Consumables | 28,600.00 |  | 30,000.00 |  |  | 58,600.00 | To cater for office Consumables for effective local governance and decentralisation |
| 9 | Rental of Office Accommodation for the Assembly | 6,648.00 |  | 30,648.00 |  |  | 37,296.00 | To provide office accommodation for Staff for local governance and decentralisation |
| 10 | Rental of Residential Accommodation for Staff | 9,258.00 |  | 48,920.00 |  |  | 58,178.00 | To provide residential accommodation for Staff for local governance and decentralisation |
| 11 | Rental of Plant and Equipment | 6,000.00 |  |  |  |  | 6,000.00 | To cater for hiring of plant for effective local governance |
| 12 | Hosting of Official Guest | 10,000.00 |  | 20,000.00 |  |  | 30,000.00 | To cater for hospitality of Official Visitors to the Assembly for decentralisation |
| 13 | Construction of 3-Bedroom Residential Accommodation |  |  | 180,727.06 |  |  | 180,727.06 | To accommodate the DCE for effective local governance |
| 14 | Construction of Office Accommodation Phase II |  |  | 202,130.42 |  |  | 202,130.42 | To provide adequate office space for staff to ensure effective local governance and decentralisation |
| 15 | Servicing and Maintenance of official vehicles | 16,000.00 |  | 35,000.00 |  |  | 51,000.00 | For Routine maintenance of official vehicles for effective local governance |
| 16 | Running Cost of official Vehicles | 13,000.00 |  | 100,000.00 |  |  | 113,000.00 | To ensure smooth running of official vehicles for effective local governance |
| 17 | Official and National Celebrations | 10,000.00 |  | 50,000.00 |  |  | 60,000.00 | To cater for statutory holiday and other official celebrations |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total BudgetGH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 18 | Utility and other charges | 21,100.00 |  | 6,000.00 |  |  | 27,100.00 | To service Utility bills of the Assembly for effective local governance |
| 19 | NALAG Dues and Other Contributions | 5,000.00 |  | 15,000.00 |  |  | 20,000.00 | Facilitate NALAG operations for effective local governance and decentralization |
| 20 | Operations and Maintenance of Assembly assets | 15,000.00 |  | 25,000.00 |  |  | 40,000.00 | For routine maintenance of Assembly's Assets for effective local governance |
| 21 | Security Management (DISEC Activities) | 10,000.00 |  | 30,000.00 |  |  | 40,000.00 | For maintenance of law and order in the district to facilitate good governance |
| 22 | MP's Constituency Support Activities [projects &programs] |  |  | 150,000.00 |  |  | 150,000.00 | Ensure MPs supports for social services provision to citizens |
| 23 | Local Travel Cost | 30,000.00 |  | 15,000.00 |  |  | 45,000.00 | To cater for transportation cost of staff in discharge of official duties |
| 24 | Administrative & Technical Meetings | 20,000.00 |  | 43,200.00 |  |  | 63,200.00 | To enhance effective participation for effective discharge of local governance and decentralisation |
| ii | Finance and Revenue Mobilization |  |  |  |  |  |  |  |
| 25 | Bank Charges | 2,000.00 |  | 2,500.00 |  |  |  | To ensure fiscal discipline for effective local governance |
| 26 | Revenue Mobilization and other treasury Activities | 15,000.00 |  | 10,000.00 |  |  | 25,000.00 | For effective Revenue Supervision and Monitoring to ensure reduction in fiscal gap |
| 27 | Internal Auditing and submission of quarterly reports | 6,418.12 |  | 5,000.00 |  |  | 11,418.12 | To ensure fiscal discipline for effective local governance |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 28 | Preparation and implementation of Revenue Improvement Plan for 2021 | 20,000.00 |  | 5,000.00 |  |  | 25,000.00 | For effective Revenue Super vision and Monitoring to ensure reduction in fiscal gap |
| iii | Planning, Budgeting and Coordination |  |  |  |  |  |  |  |
| 29 | Popular participation/Town Hall meetings | 10,000.00 |  | 20,000.00 |  |  | 30,000.00 | To ensure the implementation of all inclusive local governance and accountability |
| 30 | Project Management | 15,000.00 |  | 25,000.00 |  |  | 40,000.00 | To facilitate the Procurement, Implementation and M&E of proj/ prog for effective Infrastructural developmet and local governance |
| 31 | Preparation of 2022-2025 Composite Budget and FFR |  |  | 40,000.00 |  |  | 40,000.00 | For Composite District Budget preparation to improve fiscal discipline |
| 32 | Preparation of 2022-2025 Medium Term Development Plan |  |  | 60,000.00 |  |  | 60,000.00 | To facilitate the preparation of 2022-2025 MTDP for effective decentralisation |
| iv | Legislative Oversights |  |  |  |  |  |  |  |
| 33 | Gazetting of District bye laws and 2021 Fee-Fixing resolution |  |  | 15,000.00 |  |  | 15,000.00 | To augment the legal basis for implementation and sanctions for effective local governance |
| 34 | Court expenses and Hiring of Assembly Barrister (Retainer Fee) | 9,500.00 |  | 25,500.00 |  |  | 35,000.00 | To cater for Legal expenses of the district for effective local governance |
| 35 | Organise General Assembly, Committee & Sub-committee Meetings | 15,140.00 |  | 79,440.00 |  |  | 94,580.00 | To organize Meetings for effective local governance |
| v | Human Resource Management |  |  |  |  |  |  |  |
| 36 | Personnel and Staff Management Activities | 6,418.72 | 437.00 |  |  |  | 6,855.72 | To monitor Staff performance for effective decentralisation |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 37 | Capacity Building (Workshops, Meetings and Skill Development) | 24,900.20 |  | 25,000.00 | 26,859.00 |  | 76,759.20 | Build the competence of staff for effective decentralisation |
| 38 | Preparation of 2022 Composite Capacity Building Plan |  |  | 10,000.00 |  |  | 10,000.00 | Build the competence of staff for high productivity for effective decentralisation |
| 39 | Personnel and Staff Management | 6,418.72 | 437.00 |  |  |  | 6,855.72 | To monitor Staff performance for effective decentralisation |
| 40 | Staff Welfare Expenses | 10,000.00 |  | 23000 |  |  | 33,000.00 | To cater for Staff welfare and motivation for effective local governance |
| 41 | Procurement of 3no. Laptops, 17no. Swivel Chairs and 4no. Executive Tables |  | 6,000.00 |  | 19,000.00 |  | 25,000.00 | To provide staff with logistics for effective Local governance |
| vi | Statistics |  |  |  |  |  |  |  |
| 42 | Valuation of Properties and Update of Socio-economic Data within the District | 6,418.72 |  | 20,000.00 |  |  | 26,418.72 | To update the Dist.'s database for reliable planning and revenue forecasting for effective local governance |
| 43 | Procurement of 2No. Laptop, Receipt Thermal printer, satellite maps and internet router |  | 4,000.00 | 5,000.00 |  |  | 9,000.00 | To provide staff with logistics for effective Local governance |
| 44 | Refresher training for 4 Statistical officers |  | 2,437.00 |  |  |  | 2,437.00 | Build the competence of staff for high productivity for effective decentralisation |
|  | Sub- total | 537,897.72 | 3,047,819.27 | 1,480,692.68 | 45,859.00 | - | 5,112,268.67 |  |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B | INFRASTRUCTURE DELIVERY AND MANAGEMENT |  |  |  |  |  |  |  |
| i | Physical and Spatial Planning |  |  |  |  |  |  |  |
| 45 | Development of Base Map for Awutu Beraku, Papase No.1 and Bawjiase |  |  | 25,000.00 |  |  | 25,000.00 | For preparation of Base maps to ensure structured spatial development |
| 46 | Update and Review of Scheme and Permitting for Papase No.2, Awutu Beraku and Bawjiase |  |  | 15,000.00 |  |  | 15,000.00 | For update, Review of Scheme and Permitting to ensure structured spatial development |
| 47 | Public Education and Sensitization on spatial planning | 4,628.08 | 6,068.00 | 5,000.00 |  |  | 15,696.08 | To promote sust'ble, spatially integrated and orderly human settlement |
| 48 | Supervision & Regulation of Spatial Developments | 5,000.00 | 5,800.00 |  |  |  | 10,800.00 | To ensure structured spatial development |
| 49 | Street Naming and Property Addressing project at Senya Beraku and Awutu Beraku |  |  | 40,000.00 |  |  | 40,000.00 | Promote sust'ble, spatially integrated and orderly human settlement |
| 50 | Procurement of GPS, Plotter and Scanner |  |  | 10,000.00 |  |  | 10,000.00 | To ensure structured spatial development |
| 51 | Acquisition and Documentation of Land for Assembly Projects |  |  | 30,000.00 |  |  | 30,000.00 | To secure landed properties of the Assembly |
| ii | Infrastructure Development |  |  |  |  |  | - |  |
| 52 | Supervision & Regulation of Infrastructure Developments | 5,628.08 | 7,500.00 |  |  |  | 13,128.08 | Promote sustainable infrastructure Development |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 53 | Capacity building and training on work activities of the Engineers |  | 3,500.00 |  |  |  | 3,500.00 | To build the capacity of the Engineers to ensure improved infrastructural delivery |
| 54 | Spot Improvement and Reshaping of 60km feeder Roads and opening up of access roads in selected Communities |  |  | 180,000.00 |  |  | 180,000.00 | Improve road network within the district for local infrastructural & economic development |
| 55 | Rehabilitation of Pobikwa-Annan Feeder road (4.9km) |  |  |  |  | 500,000.00 | 500,000.00 | Improve road network within the district for local infrastructure & economic dev’t |
| 56 | Procurement of 1no. Laptop Computer, Scanner, Binding machine, Measuring tools and other office Consumables | 4,000.00 | 4,580.00 |  |  |  | 8,580.00 | To provide staff with logistics for infrastructural development |
| 57 | Dredging and Construction of 1No. Footbridge at Ponpong |  |  |  | 180,000.00 |  | 180,000.00 | To improve the drainage system in the District for infrastructural development |
| 58 | Construction of 5No. culverts at Obrachire ( 2), Bawjiase, Ankwando and Akrapa |  |  |  | 207,233.10 |  | 207,233.10 | To improve the drainage system in the District for infrastructural development |
| 59 | Extension of Ghana Water Company water pipelines at Awutu Beraku |  |  | 50,000.00 | 153,958.93 |  | 203,958.93 | Provide portable drinking water for beneficiary communities for improved infrastructural delivery |
| 60 | Construction 2No. Boreholes at Mbofrakrom and Obaakoasem |  |  | 55,479.92 |  |  | 55,479.92 | Provide portable drinking water for beneficiary communities for improved infrastructural delivery |
|  | Sub- total | 19,256.16 | 27,448.00 | 410,479.92 | 541,192.03 | 500,000.00 | 1,498,376.11 |  |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C | SOCIAL SERVICES DELIVERY |  |  |  |  |  |  |  |
| i | Education and Youth Development |  |  |  |  |  |  |  |
| 61 | Scholarship/Bursary to Needy but brilliant Student |  |  | 20,000.00 |  |  | 20,000.00 | Ensure all inclusive access to education at all levels |
| 62 | Support Science, Technology and Mathematics Education fair and participate in Regional Clinics |  |  | 10,000.00 |  |  | 10,000.00 | Promote interest in the study of Science, Technology and Mathematics for quality education |
| 63 | Support GES Activities (GSFP, DEOC etc) |  |  | 25,000.00 |  |  | 25,000.00 | Encourage interest in quality education to ensure social services delivery |
| 64 | Support District BECE Mock Exams |  |  | 27,000.00 |  |  | 27,000.00 | Encourage interest in quality education to ensure social services delivery |
| 65 | My First Day at school | 6,418.72 |  | 5,000.00 |  |  | 11,418.72 | Encourage interest in quality education to ensure social services delivery |
| 66 | MPs Constituency Support for Education Related Programmes |  |  | 75,000.00 |  |  | 75,000.00 | Encourage interest in quality education to ensure social services delivery |
| 67 | MPs Constituency Support for Education Related Projects |  |  | 75,000.00 |  |  | 75,000.00 | Enhance quality teaching and learning at all levels in the district |
| 68 | Construction of 1No.4 unit classroom block with ancillary facilities at Bawjiase D/A |  |  | 111,718.60 |  |  | 111,718.60 | Enhance quality teaching and learning at all levels in the district |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 68 | Procurement of 500no. Dual & 250no. Mono Desk, 20no.Executive Tables and Chaires & 10no. Desktop Computers for Schools |  |  | 480,810.55 |  |  | 480,810.55 | Enhance quality teaching and learning at all levels in the district |
| 69 | Renovation of 3-unit Classroom Block at Senya D/A JHS |  |  |  | 152,000.00 |  | 152,000.00 | Enhance quality teaching and learning at all levels in the district |
| 70 | Renovation of 1no 4unit classroom Block and office at Awutu Senya |  |  |  | 56,688.86 |  | 56,688.86 | Enhance quality teaching and learning at all levels in the district |
| 71 | Construction of Fence Wall at Salvation Army Sch. At Senya Beraku |  |  | 124,368.8 |  |  | 124,368.8 | Enhance quality teaching and learning at all levels in the district |
| ii | Health Delivery |  |  |  |  |  |  |  |
| 72 | Education, Sensitization and Monitoring of HIV/AIDS related activities |  |  | 19,781.80 |  |  | 19,781.80 | Reduce the HIV/AIDS menace in the District |
| 73 | Support for Malaria and Epidemic Control |  |  | 19,781.80 |  |  | 19,781.80 | Reduce/eradicate malaria infections and hedge against epidemic outbreaks |
| 74 | Renovation of Staff Quarters, Bontrase Health Centre |  |  | 69,412.30 |  |  | 69,412.30 | Provide accommodation for Health Staff to improve health care delivery in the district |
| 75 | Construction of 1No. Semi-detached Nurses quarters at Awutu Beraku |  |  |  | 384,000.00 |  | 384,000.00 | Provide accommodation for Health Staff to improve health care delivery in the district |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 76 | Construction of NHIS office accommodation at Awutu Beraku | 116,514.33 |  |  |  |  | 116,514.33 | Provide office space for staff to improve health care delivery in the district |
| 77 | Extension and supply of Electricity to CHPS compounds at Ofadaa |  |  | 35,000.00 |  |  | 35,000.00 | To improve quality health care delivery in the district |
| 78 | MPs Constituency Support for Health Related Programmes |  |  | 75,000.00 |  |  | 75,000.00 | To improve quality health care delivery in the district |
| 79 | MPs Constituency Support for Health Related Projects |  |  | 75,000.00 |  |  | 75,000.00 | To improve quality health care delivery in the district |
| 80 | Rehabilitation of CHPS Compound at Mayenda, and Okwampa & Tawiakwah |  |  | 103,401.33 |  |  | 103,401.33 | To improve quality health care delivery in the district |
| 81 | Support for health related Activities | 6,418.72 |  | 30,000.00 |  |  | 36,418.72 | To improve quality health care delivery in the district |
| 81 | Construction of Ambulance bay at Awutu Beraku |  |  |  | 204,203.21 |  | 204,203.21 | To improve quality health care delivery in the district |
| 82 | Covid-19 Response Activities | 20,000.00 |  | 30,000.00 |  |  | 50,000.00 | To cater for covid-19 response strategies |
| 83 | Acquisition of Land for Final Waste Disposal at Senya Beraku |  |  | 40,000.00 |  |  | 40,000.00 | Receptacle for refuse generated in District to ensure hygienic Environment |
| 84 | Purchase of Sanitary Tools | 10,000.00 |  | 10,000.00 |  |  | 20,000.00 | Ensure hygienic Environment |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 85 | Sanitation Improvement Package (Zoomlion) |  |  | 170,200.00 |  |  | 170,200.00 | Ensure hygienic Environment |
| 86 | Maintenance of Final Disposal site |  |  | 25,000.00 |  |  | 25,000.00 | Ensure hygienic Environment |
| 87 | Support Quarterly clean up exercise | 10,000.00 |  | 10,000.00 |  |  | 20,000.00 | Ensure hygienic Environment |
| 88 | Procure ID cards for Environmental Health and Revenue field staff | 7,000.00 |  |  |  |  | 7,000.00 | For easy identification and prevention of conflicts in discharge of duties |
| 89 | Fumigation (Source deduction) |  |  | 161,000.00 |  |  | 161,000.00 | To ensure hygienic Environment in the district |
| 90 | Purchase of Disinfectants, Insecticides, and Repellants [Local Fumigation] |  |  | 4,000.00 |  |  | 4,000.00 | To fumigate dumping sites and public places to ensure hygienic Environment |
| 91 | Screening of food vendors in the District | 2,500.00 |  |  |  |  | 2,500.00 | To ensure food hygiene and safety within the District |
| 92 | Construction of 1No. 32 Seater w/c at Awutu Beraku |  |  | 143,124.98 |  |  | 143,124.98 | To ensure hygienic Environment in the district |
| 93 | Construction of 1No 12 seater w/c at Bonsueku |  |  | 78,259.63 |  |  | 78,259.63 | To ensure hygienic Environment in the district |
| 94 | Clearing of Refuse and Gravelling at Bontrase market |  |  | 166,140.99 |  |  | 166,140.99 | To ensure hygienic Environment in the district |
| 95 | Solid and Liquid Waste Management | 27,595.14 |  | 27,093.31 |  |  | 54,688.45 | To ensure hygienic Environment in the district |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 96 | Support Dist. Sanitation and Hygiene Advocacy Team (DSHAT) | 10,000.00 |  | 10,000.00 |  |  | 20,000.00 | To ensure hygienic Environment in the district |
| 97 | Rehabilitation of 1no. slaughter slab at Bawjiase |  |  | 15,000.00 |  |  | 15,000.00 | For wholesome meat production to ensure food hygiene |
| iii | Social Welfare and Community Development |  |  |  |  |  |  |  |
| 98 | Persons with Disability (PWD) – Procurement of start-up items |  |  | 80,000.00 |  |  | 80,000.00 | Establish efficient and effective social protection system |
|  | PWD- Meetings and others |  |  | 18,690.80 |  |  | 18,690.80 | Establish efficient and effective social protection system |
|  | PWD- Financial assistance |  |  | 20,000.00 |  |  | 20,000.00 | Establish efficient and effective social protection system |
| 99 | Undertake Child Rights Promotion & Protection Activities |  | 4,200.00 |  |  |  | 4,200.00 | Establish efficient and effective social protection system |
| 100 | Gender Empowerment and Mainstreaming |  | 686.00 | 10,000.00 |  |  | 10,686.00 | To mainstream and empower gander for effective social protection system |
| 101 | Support for LEAP Administration | 2,000.00 |  |  |  |  | 2,000.00 | Establish effective social protection system |
| 102 | Family Tribunal court meetings and probation |  | 200.00 |  |  |  | 200.00 | Establish efficient and effective social protection system |
| 103 | Skill training for CBOs Women groups | 1,500.00 | 2,000.00 |  |  |  | 3,500.00 | Establish effective social protection system |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development PartnersGH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 104 | Monitor NGO and Day Care Centre operations within the District | 1,011.70 | 1,800.00 |  |  |  | 2,811.70 | Monitor NGO and Day Care Centre to ensure effective social protection system |
| 105 | Home visit to Vulnerable in 20 selected Communities | 1,000.00 | 1,000.00 |  |  |  | 2,000.00 | Establish effective social protection system |
| 106 | Organise 36 Community mass meetings and study group | 511.50 | 2,000.00 |  |  |  | 2,511.50 | Establish efficient and effective social protection system |
| 107 | Refresher training for 12 officers |  | 1,887.00 |  |  |  | 1,887.00 | Establish effective social protection system |
|  | Sub- total | 222,470.11 | 13,773.00 | 2,399,784.89 | 796,892.07 | - | 3,432,920.07 |  |
| D | ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| i | Trade and Industry |  |  |  |  |  |  |  |
| 108 | Train potential and Existing Entrepreneurs in various economic ventures | 6,418.72 |  | 20,000.00 |  |  | 26,418.72 | Encourage value addition to raw materials to improve local economy |
| 109 | Construction of 2No. Shed for Cassava Mill at Bontrase and Saakwa |  |  |  | 53,967.10 |  | 53,967.10 | Provide economic infrastructure for local economic development |
| 110 | Construction of Office Accommodation for District Business Advisory Centre (BAC) | 53,675.95 |  |  |  | 270,800.00 | 324,475.95 | Provide office accommodation for staff for local economic development |
| 111 | Procurement of 200No. Service (Low tension) Poles for Electricity Extension |  |  |  | 120,000.00 |  | 120,000.00 | Provide economic infrastructure for local economic development |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development PartnersGH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 111 | Construction of mini Market / Durbar grand at Bibianiha |  |  | 72,093.31 |  |  | 72,093.31 | Provide economic infrastructure for local economic development |
| 112 | Construction of 3No. Market Shed at Awutu Beraku |  |  |  | 42,498.87 |  | 42,498.87 | Provide economic infrastructure for local economic development |
| 113 | Support for tourism |  |  | 8,000.00 |  |  | 8,000.00 | Promote tourism to improve local economy |
| 114 | Construction of 3no. additional market sheds at Bontrase |  |  |  | 145,665.93 |  | 145,665.93 | Provide economic infrastructure for local economic development |
| ii | Agricultural Development |  |  |  |  |  |  |  |
| 115 | Farmers Day Celebration |  |  | 30,000.00 |  |  | 30,000.00 | Motivate farmers to increase food productivity for local economy development |
| 116 | Provide extension Services to Farmers |  | 16,000.00 |  |  | 71,500.00 | 87,500.00 | Provide technical advice to farmers to increase food productivity for economic dev't |
| 117 | Monitoring of Planting and Rearing for Food and Jobs |  |  | 10,000.00 |  |  | 10,000.00 | Increase food production, Security and income of farmers to improve local economy |
| 118 | Maintenance and Running Cost of official vehicle and Motorbikes |  |  |  |  | 39,310.00 | 39,310.00 | Maintenance of Assets for fieldwork to enhance economic development |
| 119 | Workshop/Seminars and meetings |  | 5,032.00 |  |  | 2,400.00 | 7,432.00 | To build capacity of staff for economic development |
| 120 | Procure and Distribute 4,000 Coconut seedlings towards Planting for Export & Rural Dev't (PERD) |  |  | 40,000.00 |  |  | 40,000.00 | To Increase food production for Local and International market to improve local economy |
| 121 | Utility and other Office consumables |  | 2,500.00 |  |  | 2,000.00 | 4,500.00 | To cater for office consumables for local economic development |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 122 | Procurement of 18no. Trackers for official motor bikes and 2no. Swivel |  | 11,900.00 |  |  |  | 11,900.00 | To provide needed logistics for Local economic development |
| 123 | Surveillance & management of diseases and pest |  | 1,000.00 |  |  |  | 1,000.00 | Increase food productivity and improve the local economy |
| 124 | Promotion and Development of Aquaculture | 4,814.04 |  |  |  |  | 4,814.04 | Promote aquaculture to improve the local economy |
| 125 | Rehabilitation of ten (10) hectare degraded communal land using coconut trees & establish ment of 20,000 seedling nursery at Oframase |  |  |  |  | 314,643.00 | 314,643.00 | Improve road network within the district for local infrastructural & economic development |
| 126 | Rehabilitation of ten (10) hectare degraded communal land using coconut trees at Fianko and one other community |  |  |  |  | 522,252.00 | 522,252.00 | Improve road network within the district for local infrastructural & economic development |
|  | Sub- total | 64,908.71 | 36,432.00 | 184,093.31 | 362,131.90 | 1,222,905.00 | 1870470.92 |  |
| E | ENVIRONMENTAL AND SANITATION MANAGEMENT |  |  |  |  |  |  |  |
| i | Disaster prevention and Management |  |  |  |  |  |  |  |
| 127 | World Disaster/Risk Reduction Day Celebration |  |  | 3,000.00 |  |  | 3,000.00 | To educate the populace on disaster management |

| S/N | LIST OF ALL PROJECTS AND PROGRAMMES | Assembly’s IGF GH₵ | GOG GH₵ | DACF GH₵ | DACF-RFG GH₵ | Development Partners GH₵ | Total Budget GH₵ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 128 | Logistics and Preparation of Disaster preparedness Plan |  |  | 2,000.00 |  |  | 2,000.00 | To educate the populace on disaster management |
| 129 | Support Disaster affected individuals |  |  | 20,000.00 |  |  | 20,000.00 | Support victims to reduce the impact on their Livelihood |
| 130 | Organize training for Disaster volunteers, Zonal Co-ordinators and Staff of the Assembly on Disaster management | 3,418.72 |  |  |  |  | 3,418.72 | Build Capacity of Society on Disaster Response Strategies |
| 131 | Public Education on Disaster Prevention and mitigation | 3,000.00 |  |  |  |  | 3,000.00 | To educate the populace on disaster management |
| ii | Natural Resource Conservation |  |  |  |  |  |  |  |
| 132 | Forest and Minerals Protection |  |  | 10,000.00 |  |  | 10,000.00 | Protect the natural resources in the district to promote natural resource conservation |
| 133 | Procurement of 200 seedlings for Tree Planting (afforestation) in all Public Schools |  |  | 10,000.00 |  |  | 10,000.00 | For afforestation in public schools for environmental protection |
| 134 | Public educate on Climate Change Response |  |  | 5,000.00 |  |  | 5,000.00 | Mitigate the effect of climate change for environmental protection |
|  | Sub- total | 6,418.72 | - | 50,000.00 | - | - | 56,418.72 |  |
|  | TOTAL | 850,951.42 | 3,125,472.27 | 4,525,050.80 | 1,187,517.00 | 1,722,905.00 | 11,970,454.49 |  |

# 20.0 SANITATION BUDGET FOR 2021

Table 13: Sanitation Budget for 2021

| Liquid Waste |  |  |
| --- | --- | --- |
| No | Name of Activity/ Project | Budget |
| 1 | Construction of 1No. 32 Seater w/c at Awutu Beraku | 143,124.98 |
| 2 | Construction of 1No 12 Seater w/c at Bonsueku | 78,259.63 |
| 3 | Implementation of other Liquid waste Management Activities | 27,344.22 |
| Solid Waste |  |  |
| No | Name of Activity/ Project | Budget |
| 1 | Purchase of Sanitary Tools | 20,000.00 |
| 2 | Sanitation Improvement Package and Fumigation (Source deductions) | 331,200.00 |
| 3 | Acquisition of land for final Waste Disposal | 40,000.00 |
| 4 | Purchase of Disinfectants, Insecticides, and Repellants | 4,000.00 |
| 5 | Support Quarterly Clean up exercises | 20,000.00 |
| 7 | Clearing of Refuse and Gravelling at Bontrase market | 166,140.99 |
| 8 | Maintenance of Final Disposal site | 25,000.00 |
| 9 | Implementation of other Liquid waste Management Activities | 27,344.22 |

# 21.0 COMPENSATION OF EMPLOYEES

Table 14: Summary of Compensation of Employees

| SUMMARY OF COMPENSATION FOR 2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| NO. | DEPARTMENT | NO. AT POST | MONTHLY SALARY | ANNUAL SALARY |
| A | ESTABLISHED POST (GOG) |  |  |  |
| 1 | Central Administration | 84 |  | 1,833,492.91 |
| 2 | Works | 7 |  | 208,456.20 |
| 3 | Agriculture | 19 |  | 480,931.02 |
| 4 | Social Welfare & Community Dev't | 14 |  | 379,674.90 |
| 5 | Physical Planning | 4 |  | 74,091.84 |
| 6 | Trade and Industry |  | - | - |
| 7 | Finance |  | - | - |
| 8 | Health |  |  |  |
|  | Sub-total for GOG Paid | 143 |  | 3,034,945.27 |
| B | NON-ESTABLISHED POST (IGF) |  |  |  |
| 9 | IGP Paid Staff | 15 |  | 110,135.96 |
| 10 | Limited Engagement and related allowances |  |  | 84,360.00 |
|  | Sub-total for IGF Paid | 15 |  | 194,495.96 |
|  | Grand Total | 158 |  | 3,229,441.23 |