## Goods
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024 -DECEMBER 2024 |  |  |  |  | Tender Documents
Source of Funding |  | GOG/DACF/DONA/IGF/DDF | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | Duration | 4 - 7 wks | 1-2 wks | 6-12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Duration | N/A | 1 wk | 1.5-3 wks | As Specified | 1-3 wks
1. Procurement of Stationery and other office materials and consumables | Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual | CR/ASDA/GDS/001/24 | 85000 | Price Quotation | Entity Tender Committee | Actual | 04/06/24 | 24/05/24 | 05/06/24 | 10/06/24 | 10/06/24 | Actual | 37102 | 17/06/24 | 17/06/24 | 27/06/24 | 28/06/24
2. Procurement of Sanitation Tool (Broom, Shevels, Detergents Gloves, Wheelbarrow, protective Cloths) | Plan | CR/ASDA/GDS/002/24 | 39000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 39000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
3. Procurement of building materials to support self help Projects/Counterpart Funding | Plan | CR/ASDA/GDS/003/24 | 147299.33 | NCT | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 147299.33 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Plan |  |  |  |  | Actual | [5 empty] | Actual
4. Procurement of Office equipments and furniture | Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual | CR/ASDA/GDS/004/24 | 12000 | Price Quotation | Head of Enitty | Actual | 14/02/24 | 07/02/24 | 14/02/24 | 15/02/24 | 15/02/21 | Actual | 10400 | 22/02/21 | 05/03/24 | 06/03/24 | 07/03/24
5. Procurement of 30 Fruit Trees seedlings and Plant in Bontrase and Bawjiase secondary Schools | Plan | CR/ASDA/GDS/005/24 | 1500 | Price Quotation | Head of Entity | Plan | 09/02/24 | 24/02/23 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 1500 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
6. Provide Uniform materials and ID cards for field staff and acquisition of Sanitary tools & Disinfectant | Plan | CR/ASDA/GDS/006/24 | 7000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 7000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Plan |  |  |  |  | Actual | [5 empty] | Actual
7. Procurement of Relief Items for Disaster Preparedness/ Managment | Plan | CR/ASDA/GDS/007/24 | 50000 | NCT | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 50000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
8. Procurement of Office Equipment and Logistics (Stationeries, 2no Office Laptop and 1no.Desktop Computer, steel Cabinet 2no. Router Executive desk with with Swivel Chair and 18no motor bikeTracker | Plan | CR/ASDA/GDS/008/24 | 12000 | NCT | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 12000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
9. Procurement of Value Books | Plan | CR/ASDA/GDS/009/24 | 76000 | Price Quotation | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 12/05/23 | Plan | 76000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  | 332799.33 |  |  | Plan | [5 empty] | Plan | 332799.33
| Actual |  | 97000 |  |  | Actual | [5 empty] | Actual | 47502
Fill gray cells only!
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024 -DECEMBER 2024 |  |  |  |  | Tender Documents
Source of Funding |  | GOG/DACF/DONA/IGF/DDF | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | Duration | 4 - 7 wks | 1-2 wks | 6-12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Duration | N/A | 1 wk | 1.5-3 wks | As Specified | 1-3 wks
10. Support Functional of the Six (6) Sub-Structures | Plan | CR/ASDA/GDS/010/24 | 85608.85 | NCT | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 85608.85 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
11. Procurement of 2no Refuse Containers and Evacuation of Refuse. | Plan | CR/ASDA/GDS/011/24 | 60000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 60000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
12. Procurement of office equipment and logistics | Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual | CR/ASDA/GDS/012/24 | 12000 | Price Quotation | Head of Entity | Actual | 09/01/24 | 03/01/24 | 12/01/24 | 16/01/24 | 17/01/24 | Actual | 4264 | 25/01/24 | 25/01/21 | 29/01/24 | 29/01/21
13. MP's Educational Support | Plan | CR/ASDA/GDS/013/24 | 20,000.00 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 20,000.00 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
14. Procurement of 2no. Motorbikes | Plan | CR/ASDA/GDS/014/24 | 15000 | NCT | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 15000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
15. Procurement of sports items (MP) | Plan | CR/ASDA/GDS/015/24 | 100000 | NCT | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 100000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
16. Procurement of 1no computers and accessories | Plan | CR/ASDA/GDS/016/24 | 3000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 3000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
17. Procurement of 2 hand held GPS device, 1 drone and accessories | Plan | CR/ASDA/GDS/017/24 | 20,000.00 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 20000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
18. Procurement of office noise level meter | Plan | CR/ASDA/GDS/018/24 | 4000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 30000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  | 287608.85 |  |  | Plan | [5 empty] | Plan | 313608.85
| Actual |  | 12000 |  |  | Actual | [5 empty] | Actual | 4264
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024 -DECEMBER 2024 |  |  |  |  | Tender Documents
Source of Funding |  | GOG/DACF/DONA/IGF/DDF | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | Duration | 4 - 7 wks | 1-2 wks | 6-12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Duration | N/A | 1 wk | 1.5-3 wks | As Specified | 1-3 wks
19. Procurement and Distribution of start-up items to support PWDs | Plan | CR/ASDA/GDS/019/24 | 50000 | NCT | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 50000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
20. Procurement of Materials (MP'S) Suport | Plan | CR/ASDA/GDS/020/24 | 240000 | NCT | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 240000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
21. Procurement of Agric Tools | Plan | CR/ASDA/GDS/021/24 | 144620 | Price Quotation | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 144,620.00 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
22. Agricultural Inputs & Tools (MP) | Plan | CR/ASDA/GDS/022/24 | 75000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 75000 | 29/03/24 | 05/04/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
23. Procurement of Sationery and other logistics | Plan | CR/ASDA/GDS/023/24 | 110000 | Price Quotation | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan |  | 29/03/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
24. Procurement of building materials | Plan | CR/ASDA/GDS/024/24 | 250000 | NTC | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 | 10/05/24 | Plan | 250000 | 29/03/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
25. Procurement of material support (MP) | Plan | CR/ASDA/GDS/025/24 | 240000 | NTC | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 20/03/24 |  | Plan |  | 29/03/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
26. Procurement Management | Plan | CR/ASDA/GDS/026/24 | 15000 | Price Quotation | Head of Entity | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 13/03/24 | 10/05/24 | Plan | 45000 | 29/03/24 | 29/03/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
27. Procurement of 150No. Hexagonal Tables and Chairs and 460No. Dual Desks | Plan | CR/ASDA/GDS/027/24 | 345660 | NTC | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 13/03/24 | 10/05/24 | Plan | 345660 | 29/03/24 | 29/03/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  | 1395280 |  |  | Plan | [5 empty] | Plan | 1150280
| Actual |  | 0 |  |  | Actual | [5 empty] | Actual | #REF!
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024 -DECEMBER 2024 |  |  |  |  | Tender Documents
Source of Funding |  | GOG/DACF/DONA/IGF/DDF | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | Duration | 4 - 7 wks | 1-2 wks | 6-12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Duration | N/A | 1 wk | 1.5-3 wks | As Specified | 1-3 wks
28. Fuel for DRIP | Plan | CR/ASDA/GDS/028/24 | 200000 | NTC | Entity Tender Committee | Plan | 09/02/24 | 23/02/24 | 13/03/24 | 13/03/24 | 10/05/24 | Plan | 200000 | 29/03/24 | 29/03/24 | 12/04/24 | 10/04/24
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  | 200000 |  |  | Plan | [5 empty] | Plan | 200000
| Actual |  | 0 |  |  | Actual | [5 empty] | Actual | #REF!

## Works
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024-DECEMBER 2024 | [5 empty] | Tender Documents
Source of Funding |  | GOG/DACF/IGF/DDF/GPSNP | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
1. .Sport Improvement and reshaping of 20km Selected Feeder Roads | Plan | CR/ASDA/WK/001/24 | 285000 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 285000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 285000
| Actual | [5 empty] | Actual | [5 empty] | Actual
2. Renovation of CHPS Compound and Nurses Quartersat Tawiakwah | Plan | CR/ASDA/WK/002/24 | 34216.5 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 34216.5 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 35005
| Actual | [5 empty] | Actual | [5 empty] | Actual
3. Part Completion of Senya Market, Repair Work on Structure 3no. Shed 2no. Lockable Stores and 1 Urban Council Office (take Over from CEDECOM | Plan | CR/ASDA/WK/003/24 | 20231.41 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 20231.41 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 20231.41
| Actual | [5 empty] | Actual | [5 empty] | Actual
4.Construction of 3 No.0.09 Dia Single Cell Pipe Culvert width(8M) and filling approaches at : Bawjiase (2No.) and Okwabena | Plan | CR/ASDA/WK/022/24 | 7139.13 | ETC | POST | ETC | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 7139.13 | 03/04/24 | 15/04/24 |  | 14/08/24 | 11/11/2024 | 7139.13
| Actual | [5 empty] | Actual | [5 empty] | Actual |  |  |  | N/A
5. Connection of Pipe-born Water to Bontrase SHS 2km stretch (2023 IGF CAPEX) | Plan | CR/ASDA/WK/004/24 | 180000 | ETC | POST | ETC | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 180000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 180000
| Actual | [5 empty] | Actual | [5 empty] | Actual
6. Deslugement of Assembly owned public toilets | Plan | CR/ASDA/WK/009/24 | 17000 | NCT | POST | ETC | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 17000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 17000
| Actual | [5 empty] | Actual | [5 empty] | Actual
7. Construction of 1no. 2-Unit KG Block with anillary and 30no. KG round tables and chairs at Yamua Nkwanta School | Plan | CR/ASDA/WK/005/24 | 556597 | NCT | POST | REGIONAL REVIEW APP | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 556597 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 540000
| Actual | [5 empty] | Actual | [5 empty] | Actual
8. Construction of NHIS office accommodation and Water stand at Awutu Beraku Phase II (IGF) | Plan | CR/ASDA/WK/006/24 | 191561.17 | Price Quotation | POST | ETC | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 191561.17 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 257072.09
| Actual | [5 empty] | Actual | [5 empty] | Actual
9. Construction of 5No. Market Shed at Bentum | Plan | CR/ASDA/WK/020/24 | 11748.9 | Price Quotation | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 11748.9 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 11748.9
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 1303494.11 |  |  |  | Plan | [5 empty] | Plan | #REF! | [5 empty] | 1353196.53
| Actual |  | 34216.5 |  |  |  | Actual | [5 empty] | Actual | 20231.41 | [5 empty] | 0
Fill gray cells only!
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024-DECEMBER 2024. | [5 empty] | Tender Documents
Source of Funding |  | GOG/DACF/IGF/DDF/GPSNP | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
10. Construction of Fence Wall at Salvation Army School at Senya Beraku | Plan | CR/ASDA/WK/006/24 | 256437 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 256437 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 256437
| Actual | [5 empty] | Actual | [5 empty] | Actual
11. Construction of Animal Pound at Bontrase and Rehabilitation of Slaughter Slab at Bawjiase (IGF Capex 2023) | Plan | CR/ASDA/WK/007/24 | 35000 | Price Quotation | POST | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 35000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 35000
| Actual | [5 empty] | Actual | [5 empty] | Actual
12. Cladding of 1no. 3-unit Classroom Block at Opembo Anglican School | Plan | CR/ASDA/WK/008/24 | 250000 | NCT | NCT | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 250000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 250000
| Actual | [5 empty] | Actual | [5 empty] | Actual
13. Construction of 1No.CHPS. With ancillary facilities at Mayenda | Plan | CR/ASDA/WK/009/24 | 480000 | NCT | NCT | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 480000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 480000
| Actual | [5 empty] | Actual | [5 empty] | Actual
14. Maintenance of Boreholes and other water system (MP) | Plan | CR/ASDA/WK/010/24 | 10000 | Price Quotation | POST | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 10000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 10000
| Actual | [5 empty] | Actual | [5 empty] | Actual
15. Construction of 2No. Waiting Sheds for Motor and Baby at Osae Krodua and Ayiresu (MP) | Plan | CR/ASDA/WK/011/24 | 22000 | NCT | POST | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 22000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 22000
| Actual | [5 empty] | Actual | [5 empty] | Actual
16.Construction of 1No. 6-Unit Classroom Block at Senya Zion A&B | Plan | CR/ASDA/WK/026/24 | 22440.74 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 22440.74 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 447924.9
| Actual | [5 empty] | Actual | [5 empty] | Actual
17. Construction of 5No.0.9 Diameter Single Cell Pipe Culvert with 8m and Filling Approaches at Obrachire(2), Bawjiase, Ankwando | Plan | CR/ASDA/WK/012/24 | 82527.11 | NCT | POST | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 82527.11 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 82527.11
| Actual | [5 empty] | Actual | [5 empty] | Actual
18. Construction of 1No. 6-Seater W/C Toilet at Bontrase Market | Plan | CR/ASDA/WK/013/24 | 93570.17 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 93570.17 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 93570.17
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 1251975.02 |  |  |  | Plan | [5 empty] | Plan | 1159447.91
| Actual |  | 0 |  |  |  | Actual | [5 empty] | Actual | 0
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024-DECEMBER 2024 | [5 empty] | Tender Documents
Source of Funding |  | GOG/DACF/IGF/DDF/GPSNP | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
19. Implement Ghana Productive Safety Net Projects (GPSNP) 4 | Plan | MLGRD/ASDA/GPSNP/FR/LIPW/ON/001/2023 | 100000 | ETC | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 100000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 100000
| Actual | [5 empty] | Actual | [5 empty] | Actual
20. Construction of 1no. 2 Bedroom Semi-detached Nurses Residential/ Quarter at Awutu Beraku (PHASE I) | Plan | CR/ASDA/WK/014/24 | 75685.36 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 75685.36 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 80000
| Actual | [5 empty] | Actual | [5 empty] | Actual
21. Maintenance of final disposal site, Assembly's Public Toilets and Desilting of Drains | Plan | CR/ASDA/WK/015/24 | 25000 | Price Quotation | POST | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 25000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 25000
| Actual | [5 empty] | Actual | [5 empty] | Actual
22. Fencing of 3-Bedroom residential accommodation at Awutu Beraku | Plan | CR/ASDA/WK/016/24 | 129453.67 | ETC | POST | Head of Entity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 129453.67 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 129453.67
| Actual | [5 empty] | Actual | [5 empty] | Actual
23. Construction of pavement at DCE's residence | Plan | CR/ASDA/WK/017/24 | 126641.5 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 146053.35 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 126641.5
| Actual | [5 empty] | Actual | [5 empty] | Actual
24. Construction of 1no. 2 Bedroom Semi-detached Nurses Residential/ Quarter at Awutu Beraku (PHASE II) | Plan | CR/ASDA/WK/018/24 | 271116.8 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 271116.8 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 271116.8
| Actual | [5 empty] | Actual | [5 empty] | Actual
25.Periodic Evacuation of Refuse Dump Site in selected communities | Plan | CR/ASDA/WK/019/24 | 110000 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 110000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 110000
| Actual | [5 empty] | Actual | [5 empty] | Actual
26.Local fumigation of public places | Plan | CR/ASDA/WK/020/24 | 30000 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 30000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 30000
| Actual | [5 empty] | Actual | [5 empty] | Actual
27. Construction of 1No. 32 seater WC at Awutu Beraku,12 seater WC at Bonsueku and mini durbar ground at Bibianiha | Plan | CR/ASDA/WK/021/24 | 71281.71 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 71281.71 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 71281.71
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 939179.04 |  |  |  | Plan | [5 empty] | Plan | 887309.18 | [5 empty] | 943493.68
| Actual |  | 0 |  |  |  | Plan | [5 empty] | Plan | 0 | [5 empty] | 0
Procurement Entity:+A124:A1A124:G197 |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024-DECEMBER 2024 | [5 empty] | Tender Documents
Source of Funding |  | GOG/DACF/IGF/DDF/GPSNP | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual |  | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
28. Construction of overhead water stand at Beraku, Bawjiase and Bontrase Markets | Plan | CR/ASDA/WK/021/24 | 12179.05 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 12179.05 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 12179.05
| Actual | [5 empty] | Actual | [5 empty] | Actual
29. Face lifting and extension of Bawjiase Market | Plan | CR/ASDA/WK/022/24 | 559790 | NCT | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 559790 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 559790
| Actual | [5 empty] | Actual | [5 empty] | Actual
30. Renovation of 3-unit classroom block at Senya DA | Plan | CR/ASDA/WK/023/24 | 15760.5 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 15760.5 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 15760.5
| Actual | [5 empty] | Actual | [5 empty] | Actual
31. Construction of CHPS at Bonsueku | Plan | CR/ASDA/WK/023/24 | 12731.98 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 12731.98 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 12731.98
| Actual | [5 empty] | Actual | [5 empty] | Actual
32. Desilting of Drains at Bawjiase and Beraku market | Plan | CR/ASDA/WK/024/24 | 10000 | ETC | POST | Head of Enity | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 10000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 10000
| Actual | [5 empty] | Actual | [5 empty] | Actual
33. Construction of 1No. 2-Bedroom Semi-detached Nurses Residential Accommodation (PHASE III) with 12No. Balustrades, 1No. Water Stand, 3No.WaterTank and Fence Wall at Awutu Beraku. | Plan | CR/ASDA/WK/025/24 | 1150000 | NCT | POST | REGIONAL REVIEW APP | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 1150000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 1150000
| Actual | [5 empty] | Actual | [5 empty] | Actual
34. Construction of 1No.1.2 Diameter double Cell Pipe Culvert (8m) and Filling of Approaches (100m) at Akrampa | Plan | CR/ASDA/WK/026/24 | 194642 | ETC | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 194642 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 194642
| Actual | [5 empty] | Actual | [5 empty] | Actual
35. Construction of Carpot and Access Road at DCD's Bungalow | Plan | CR/ASDA/WK/027/24 | 100940.07 |  | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 100940.07 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 100940.07
| Actual | [5 empty] | Actual | [5 empty] | Actual
36. DRIP-Reshaping and creation of access roads | Plan | CR/ASDA/WK/028/24 | 300000 |  | POST | Entity Tender Committee | Plan | 15/04/24 | 19/04/24 | 25/03/24 | 27/03/24 | 28/03/24 | Plan | 300000 | 03/04/24 | 15/04/24 | N/A | 14/08/24 | 11/11/2024 | 300000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 2056043.6 |  |  |  | Plan | [5 empty] | Plan | 2356043.6 | [5 empty] | 2356043.6
| Actual |  | 0 |  |  |  | Actual | [5 empty] | Actual | 0 | [5 empty] | 0
AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2024-DECEMBER 2024 | [5 empty] | Tender Documents
Source of Funding |  | GOG/DACF/IGF/DDF/GPSNP | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual |  | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 0 |  |  |  | Plan | [5 empty] | Plan | 0 | [5 empty] | 0
| Actual |  | 0 |  |  |  | Actual | [5 empty] | Actual | 0

## Consultants
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period |  | JANUARY 2024- DECEMBER 2024
Source of Funding |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
1. Development of Base Map for Senya Beraku | Plan | CR/ASDA/CS/001/24 | 20000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 |  | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 20000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
2. Maintenance of Disposal site at Bonsueku | Plan | CR/ASDA/CS/002/24 | 30000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 50000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 80000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
3. Organize clean up exercises | Plan | CR/ASDA/CS/003/24 | 40000 | Consultants Qualification | ETC | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 40000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 40000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
4. Operations and Maintenance of Assembly Vehicles and Assest | Plan | CR/ASDA/TS/004/24 | 40000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 89100 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 129100
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
5. Documentation and inspection of Assembly Lands | Plan | CR/ASDA/CS/005/24 | 54774.63 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 20000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 54774.63
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
6. MPs support for Sanitation | Plan | CR/ASDA/CS/006/24 | 30000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 30000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 30000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
7. Sensitation on providing a safe and protective environment for the children in five communities | Plan | CR/ASDA/CS/007/24 | 3700 | Least-Cost selection | ETC | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 3700 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 3700
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
8. 1no skill training for 50 PWDs in 2 local and urban areas | Plan | CR/ASDA/TS/008/24 | 5000 | Least-Cost selection | ETC | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/20234 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 10000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 5000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
9. Organize technical sub committee spatial planning committee meetings | Plan | CR/ASDA/TS/009/24 | 68328 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2023 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 68328 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 68328
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  | 291802.63 |  |  | Plan | [7 empty] | Plan |  |  |  | 311128 |  |  | Plan |  |  |  | 430902.63
| Actual |  | 0 |  |  | Actual | [7 empty] | Actual |  |  |  | 0 |  |  | Actual |  |  |  | 0
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period |  | JANUARY 2024 - DECEMBER 2024
Source of Funding |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
10. Ground truthing, Street Naming, plotting of site plans in Awutu Beraku | Plan | CR/ASDA/TS/010/24 | 50000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 50000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 50000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
11. Running cost of office vehicles | Plan | CR/ASDA/TS/011/24 | 185000 | Least-Cost selection | ETC | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 200000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 185000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
12. Sanitation improvement package (Zoomlion) | Plan | CR/ASDA/TS/012/24 | 100000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 161000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 161000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
13. Workshop/Training and seminars | Plan | CR/ASDA/TS/013/24 | 70000 | Least-Cost selection | ETC | Plan | 14/02/24 | 22/02/2024 | 12/05/20243 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 90000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 162000
| Actual |  |  |  |  | Actual | 14/02/24 | [6 empty] | Actual | [6 empty] | Actual
14.screening of Food Vendors in the District | Plan | CR/ASDA/TS/014/24 | 15000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 |  | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 15000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
15. Organise Training in GIS Land use and Spatial Planning and Drone Operation | Plan | CR/ASDA/TS/015/24 | 2000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 2000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 2000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
16. Establishment of centralized departmental database | Plan | CR/ASDA/TS/016/24 | 16800 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 8000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 8000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
17.. Train 160 graduate Apprentices in Start Your Business | Plan | CR/ASDA/TS/017/24 | 4000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 6000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 6000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
18. Training of GJSP applicants | Plan | CR/ASDA/TS/018/24 | 1500 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 26/05/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 1500 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 1500
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  | 444300 |  |  | Plan | [7 empty] | Plan |  |  |  | 518500 |  |  | Plan |  |  |  | 590500
| Actual |  | 0 |  |  | Actual | [7 empty] | Actual |  |  |  | 0 |  |  | Actual |  |  |  | 0
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period |  | JANUARY 2024 - DECEMBER 2024
Source of Funding |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
19. Maintenance and Running Cost of Official Vehicle and Motor Bike | Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan | N/A |  |  | 12000
| Actual | CR/ASDA/TS/019/24 | 12000 | Least-Cost selection | Head of Entity | Actual | 17/04/24 | 17/04/24 | 23/04/24 | 26/04/24 | 23/04/24 | 26/04/24 | 26/04/24 | Actual | 26/o4/24 | 10/05/24 | 10/05/24 | 79182.7 | 03/05/24 | 03/05/24 | Actual |  | 28/01/24 | 29/01/24
20. Buisiness counscelling for 50 trained client | Plan | CR/ASDA/TS/020/24 | 1500 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 1500 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 1500
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
21. Training of youth across the District on various business ventures | Plan | CR/ASDA/TS/021/24 | 2500 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 2500 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 2500
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
22. Private sector skill training and finanial support (MP) | Plan | CR/ASDA/TS/022/24 | 190000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 190000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 190000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
23. Organize arts workshop for Bontrase and Bawjiase SHS | Plan | CR/ASDA/TS/023/24 | 4391.21 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 4391.21 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 4391.21
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
24. Establish and monitor 20,000 coconut seedlings under planting for export and rural development(PERD) | Plan | CR/ASDA/TS/024/24 | 30000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 30000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 30000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
25. Utility and office maintenance | Plan | CR/ASDA/TS/025/24 | 2000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 21/07/2024 | 18/08/2024 | 2000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 2000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
26. Transportation of materials | Plan | CR/ASDA/TS/025/24 | 21750 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 21/07/2024 | 18/08/2024 | 21750 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 21750
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
27. Education on climate change in 15 farming communities in the District | Plan | CR/ASDA/TS/025/24 | 6000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 21/07/2024 | 18/08/2024 | 6000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 6000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  | 258141.21 |  |  | Plan | [7 empty] | Plan |  |  |  | 258141.21 |  |  | Plan |  |  |  | 270141.21
| Actual |  | 12000 |  |  | Actual | [7 empty] | Actual |  |  |  | 79182.7 |  |  | Actual |  |  |  | 0
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period |  | JANUARY 2024 - DECEMBER 2024
Source of Funding |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
28. Train 24 staff and 10 Disaster volunteer Groups | Plan | CR/ASDA/TS/026/24 | 2000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 2000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 2000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
29. Support towards documentation and development of Apra forest | Plan | CR/ASDA/TS/027/24 | 6000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 50000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 56000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
30. Maintenance of DRIP equipment | Plan | CR/ASDA/TS/028/24 | 200000 | Least-Cost selection | Head of Entity | Plan | 14/02/24 | 22/02/2024 | 12/05/2024 | 26/05/2024 | 16/06/2024 | 23/06/2024 | 06/07/2024 | Plan | 21/07/2024 | 04/08/2024 | 18/08/2024 | 200000 | 24/08/2024 | 08/09/2024 | Plan | N/A | 11/10/2024 | 09/11/2024 | 200000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  | 208000 |  |  | Plan | [7 empty] | Plan |  |  |  | 252000 |  |  | Plan |  |  |  | 258000
| Actual |  | 0 |  |  | Actual | [7 empty] | Actual |  |  |  | 0 |  |  | Actual |  |  |  | 0