## GOODS.
AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: | JANUARY 2025 -DECEMBER 2025
Source of Funding | GOG/DACF/DONOR/IGF/DACF-RFG |  | BASIC DATA |  |  |  | Tender Documents | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | Duration | 4 - 7 wks | 1-2 wks | 6-12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Duration | N/A | 1 wk | 1.5-3 wks | As Specified | 1-3 wks
1. Procurement of Sanitation Tools By Hon MP | Plan | CR/ASDA/GDS/001/25 | 20000 | Price Quotation | Head of Entity | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 20/03/25 | 12/05/25 | Plan | 20000 | 29/03/25 | 05/04/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
2.Acquisition of office Facilities,supplies Accessories | Plan | CR/ASDA/GDS/002/25 | 187022.05 | Price Quotation | ETC | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 20/03/25 | 10/05/25 | Plan | 187022.05 | 29/03/25 | 05/04/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
3. Promotion of sports by HON .MP | Plan | CR/ASDA/GDS/003/25 | 40000 | Price Quotation | Head of Entity | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 20/03/25 | 10/05/25 | Plan | 40000 | 29/03/25 | 05/04/25 | 12/04/25 | 10/04/25
| Plan |  |  |  |  | Actual | [5 empty] | Actual
4.Procurement of Building Materials by Hon .MP | Plan | CR/ASDA/GDS/004/25 | 210000 | NCT | ETC | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 20/03/25 | 10/05/25 | Plan | 210000 | 29/03/25 | 05/04/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
5. Procurement of Agricultural Inputs & Tools by Hon.MP | Plan | CR/ASDA/GDS/005/25 | 50000 | Price Quotation | Head of Entity | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 20/03/25 | 10/05/25 | Plan | 50000 | 29/03/25 | 05/04/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
6.Self help/counterpart funding of projects | Plan | CR/ASDA/GDS/006/25 | 165090.3 | Price Quotation | ETC | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 20/03/25 | 10/05/25 | Plan | 165090.3 | 29/03/25 | 05/04/25 | 12/04/25 | 10/04/25
| Plan |  |  |  |  | Actual | [5 empty] | Actual
7.Birth and Death Registry Administrative Recurrent Expenditure | Plan | CR/ASDA/GDS/007/25 | 13000 | Price Quotation | Head of Entity | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 13/03/25 | 10/05/25 | Plan | 13000 | 29/03/25 | 29/03/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
8.Works Department Recurrent Expenditure | Plan | CR/ASDA/GDS/008/25 | 32000 | Price Quotation | Head of Entity | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 13/03/25 | 10/05/25 | Plan | 32000 | 29/03/25 | 29/03/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
9. Procurement of sanitary tools and detergents | Plan | CR/ASDA/GDS/009/25 | 38,000.00 | Price Quotation | Head of Enitty | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 13/03/25 | 10/05/25 | Plan | 38,000.00 | 29/03/25 | 29/03/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: | JANUARY 2025-DECEMBER 2025
Source of Funding | GOG/DACF/DONOR/IGF/DACF-RFG |  | BASIC DATA |  |  |  | Tender Documents | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | Duration | 4 - 7 wks | 1-2 wks | 6-12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Duration | N/A | 1 wk | 1.5-3 wks | As Specified | 1-3 wks
10. Desilting of drains , maintenance of final disposal site, rehabilitation of slaughter slab evacuation of refuse, dislodging of toilets | Plan | CR/ASDA/GDS/010/25 | 25000 | Price Quotation | Head of Enitty | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 13/03/25 | 10/05/25 | Plan | 25000 | 29/03/25 | 29/03/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
11. Procurement of Communal Refuse Containers | Plan | CR/ASDA/GDS/011/25 | 60000 | Price Quotation | ETC | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 13/03/25 | 10/05/25 | Plan | 60000 | 29/03/25 | 29/03/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
12.Procurement of 2 Hand held GPS device, 1 Drone and Accessories | Plan | CR/ASDA/GDS/012/25 | 20000 | Price Quotation | Head of Enitty | Plan | 09/02/25 | 23/02/25 | 13/03/25 | 13/03/25 | 10/05/25 | Plan | 20000 | 29/03/25 | 29/03/25 | 12/04/25 | 10/04/25
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  |  |  |  | Plan | [5 empty] | Plan
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Total Cost | Plan |  | 0 |  |  | Plan | [5 empty] | Plan | 0
| Actual |  | 80000 |  |  | Actual | [5 empty] | Actual | 80000

## Works.
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2025 -DECEMBER 2025
Source of Funding |  | GOG/DACF/IGF/DACF-RFG/GPSNP | BASIC DATA |  |  |  |  | Tender Documents | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
1. .Spot Improvement of Feeder Roads | Plan | CR/ASDA/WK/001/25 | 1060000 | ETC | POST | Entity Tender Committee | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 1060000 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 1060000
| Actual | [5 empty] | Actual | [5 empty] | Actual
2. Renovation of CHPS Compound and Nurses Quarters at Tawiakwah | Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | CR/ASDA/WK/008/21 | 34216.5 | Price Quotation | POST | Head of Entity | Actual | 03/06/21 | 18/06/21 | 18/06/21 | 23/06/21 | 23/06/21 | Actual | 88006.6 | 07/07/21 | 14/07/21 | N/A |  |  | 88006.6
3.Construction of 1 No.1.2 Diameter double Cell Pipe Culvert (8M) and filling approaches 100m at Akrampa | Plan | CR/ASDA/WK/003/25 | 194642 | ETC | POST | Entity Tender Committee | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 194642 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 194642
| Actual | [5 empty] | Actual | [5 empty] | Actual
4. Construction of NHIS office at Awutu Beraku Phase II | Plan | [5 empty] | Plan | 15/04/25 |  |  |  |  | Plan |  |  |  |  | 14/08/25 | 11/11/2025
| Actual | CR/ASDA/WK/014/24 | 66210.72 | Price Quotation | POST | Head of Entity | Actual |  | 21/10/22 | 11/11/22 |  |  | Actual | 257072.09 | 28/11/22 | 19/12/22 | N/A |  |  | 257072.09
5. Construction of Fence Wall at Salvation Army School at Senya Beraku | Plan | CR/ASDA/WK/005/25 | 250000 | NCT | POST | Entity Tender Committee | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 250000 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 250000
| Actual | [5 empty] | Actual | [5 empty] | Actual
6. Construction of 5No.0.9 Diameter Single Cell Pipe Culvert with 8m and Filling Approaches at Obrachire(2), Ankwando and Akrampa Retention | Plan | CR/ASDA/WK/006/25 | 2116.84 | Price Quotation | POST | Head of Entity | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 2116.84 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 2116.84
| Actual | [5 empty] | Actual | [5 empty] | Actual
7. Construction of 1No. 6-Seater W/C Toilet at Bontrase Market | Plan | [5 empty] | Plan | [5 empty] | Plan |  |  |  |  | 14/08/25 | 11/11/2025
| Actual | CR/ASDA/WK/021/21 | 14711.49 | Price Quotation | POST | Head of Entity | Actual | 3/11/21 | 3/11/21 | 16/11/21 | 16/11/21 |  | Actual | 162140.56 | 30/11/2102/12/21 |  | N/A |  |  | 162140.56
8. Construction of Culvert at Akrampa | Plan | CR/ASDA/WK/008/25 | 220000 | NCT | POST | Entity Tender Committee | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 220000 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 220000
| Actual | [5 empty] | Actual | [5 empty] | Actual
h
9. Fencing of 3-Bedroom residential accommodation at Awutu Beraku | Plan | CR/ASDA/WK/009/25 | 59453.67 | Price Quotation | POST | Head of Entity | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 59453.67 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 59453.67
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 1901351.22 |  |  |  | Plan | [5 empty] | Plan | [6 empty] | 2293431.76
| Actual | [5 empty] | Actual | [5 empty] | Actual
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2025-DECEMBER 2025. | [5 empty] | Tender Documents
Source of Funding |  | GOG/DACF/IGF/DACF-RFG/GPSNP | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
10. Construction of pavement and Carport and Access road for 3-Bedroom residential accommodation at Awutu Beraku | Plan | [5 empty] | Plan |  |  |  | 27/03/25 | 28/03/25 | Plan
| Actual | CR/ASDA/WK/017/24 | 100940.07 | ETC | POST | Entity Tender Committee | Actual | 10/04/24 | 17/04/24 | 17/04/24 |  |  | Actual | 100940.07 | 06/05/24 | 03/06/24 | N/A |  |  | 100940.07
11. Construction of 1No. 32 seater WC at Awutu Beraku,12 seater WC at Bonsueku and mini durbar ground at Bibianiha | Plan | [5 empty] | Plan |  |  |  |  | 28/03/25 | Plan |  |  |  |  | 14/08/25 | 11/11/2025 | 71281.71
| Actual | ASDA/DCAF/W/CB/00/2016 | 71281.71 | Price Quotation | POST | Head of Enity | Actual | 22/08/16 | 09/09/16 | 09/09/16 | 09/09/16 |  | Actual | 450477.92 | 19/09/16 | 28/09/24 | N/A |  |  | 450477.92
12. Construction of 1No.CHPS at Bonsueku | Plan | CR/ASDA/WK/012/25 | 12731.98 | Price Quotation | POST | Head of Enity | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 12731.98 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 12731.98
| Actual | [5 empty] | Actual | [5 empty] | Actual
13.Construction of 1No.2Bedroom semi Detached Nurses Residential Accommodation (PHASE III) with 12No.Balustrades,1No.Water stand,3No.Water tanks and Fence Wall at Awutu Beraku. | Plan | [5 empty] | Plan | [5 empty] | Plan |  | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025
| Actual | CR/ASDA/WK/025/24 | 1150000 | NCT | POST | Entity Tender Committee | Actual | 24/10/24 | 24/10/24 | 12/11/24 | 12/11/24 | 12/11/24 | Actual | 1149701 | 05/12/2426/11/24 |  | N/A |  |  | 1149701
14.Construction of pavement of DCD's Residence at Awutu Beraku | Plan | [5 empty] | Plan | [5 empty] | Plan |  |  |  |  | 14/08/25 | 11/11/2025
| Actual | CR/ASDA/WK/017/24 | 22143.36 | Price Quotation | POST | Head of Entity | Actual | 10/04/24 | 17/04/24 | 17/04/24 |  |  | Actual | 199693.56 | 03/05/24 | 24/05/24 | N/A |  |  | 199693.56
15.Construction of 1no.Area council Office at Bontrase | Plan | CR/ASDA/WK/015/25 | 700906.31 | NCT | RTC | Entity Tender Committee | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 700906.31 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 700906.31
| Actual | [5 empty] | Actual | [5 empty] | Actual
16. Rehabilitation of Market sheds and stores at Bawjiase | Plan | CR/ASDA/WK/016/25 | 430000 | NCT | POST | Entity Tender Committee | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 430000 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 430000
| Actual | [5 empty] | Actual | [5 empty] | Actual
17. Construction of 1No. 23.82M Concrete Footbridge at Bonstrase Market-Awutu Beraku | Plan | [5 empty] | Plan | [5 empty] | Plan | [5 empty] | 11/11/2025
| Actual | CR/ASDA/WK/013/24 | 231498.07 | NCT | POST | Entity Tender Committee | Actual |  | 24/10/24 | 24/10/24 | 24/10/24 |  | Actual | 114407.98 | 20/11/24 | 03/12/24 | N/A |  |  | 114407.98
18..Construction of 1No.32-Seater W/C at Bontrase Market | Plan | CR/ASDA/WK/018/25 | 14711.49 | Price Quotation | POST | Head of Enity | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 14711.49 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 14711.49
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan |  | 2734212.99 |  |  |  | Plan | [5 empty] | Plan | 2,573,996.63 | [5 empty] | 2,573,996.63
| Actual | [5 empty] | Actual | [5 empty] | Actual
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2025-DECEMBER 2025.
Source of Funding |  | GOG/DACF/IGF/DACF-RFG/GPSNP | BASIC DATA |  |  |  |  | Tender Documents | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | 4 - 7 wks | 1.5 - 2 wks | 6 - 12 wks | 2 - 4 wks | 1.5 - 3 wks | Duration | N/A | 1 wk | 1.5-3 wks | 1 - 4 wks | As specified
19. Maintenance of Assembly Residential /Office Buildings | Plan | CR/ASDA/WK/019/25 | 16500 | Price Quotation | POST | Head of Enity | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 16500 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 16500
| Actual | [5 empty] | Actual | [5 empty] | Actual
20. Rehabilitation of Obrachire-Kukurabi Feeder Road (4.5Km) GPSNP 4 | Plan | CR/ASDA/WK/020/25 | 1071187.76 | NCT | POST | RTC | Plan | 15/04/25 | 19/04/25 | 25/03/25 | 27/03/25 | 28/03/25 | Plan | 1071187.76 | 03/04/25 | 15/04/25 | N/A | 14/08/25 | 11/11/2025 | 1071187.76
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
| Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual
Total Cost | Plan | [5 empty] | Plan | [5 empty] | Plan
| Actual | [5 empty] | Actual | [5 empty] | Actual

## Consultancy
Procurement Entity: |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period: |  | JANUARY 2025- DECEMBER 2025
Source of Funding: |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
1. Documentation and Inspection of Assembly Lands | Plan | CR/ASDA/CS/001/25 | 60000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/2025 | 12/05/2025 | 26/05/2025 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 60000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 60000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
2. Local Sanitation Management | Plan | CR/ASDA/TS/002/25 | 224000 | Least-Cost selection | ETC | Plan | 14/02/25 | 22/02/2025 | 12/05/2025 | 26/05/2025 | 26/05/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 224000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 224000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
3. Maintenance and Running Cost of Official Vehicles | Plan | CR/ASDA/TS/003/25 | 295000 | Least-Cost selection | NCT | Plan | 14/02/25 | 22/02/2025 | 12/05/2025 | 26/05/2025 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 295000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 295000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
4. Capacity Building in Employable skills/Support for BAC | Plan | CR/ASDA/TS/004/25 | 50000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/2025 | 12/05/2025 | 26/05/2025 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 50000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 50000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
5. Support for MSMSEs/Organisation of Meetings | Plan | CR/ASDA/TS/005/25 | 20000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/2025 | 12/05/2025 | 26/05/2025 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2024 | 04/08/2025 | 18/08/2025 | 20000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 20000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
6. Support to Drivers/Riders' for Acquisition of License by the Hon. MP | Plan | CR/ASDA/TS/006/25 | 70000 | Least-Cost selection | ETC | Plan | 14/02/24 | 22/02/2025 | 12/05/2025 | 26/05/2025 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 70000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 70000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
7. Support for Women in the Business - Hon. MP | Plan | CR/ASDA/TS/007/25 | 55000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/2025 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 55000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 55000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
8.Trainings, Field Demonstrations, and Procurement of Seedlings to Improve Crop Production and Facilitate PERD | Plan | CR/ASDA/TS/008/25 | 130000 | Least-Cost selection | ETC | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 130000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 130000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
9.National Farmers' &Fishermen Day Celebration | Plan | CR/ASDA/TS/009/25 | 85000 | Least-Cost selection | ETC | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 85000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 85000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Actual |  |  |  |  | Actual | [7 empty] | Actual |  |  |  | 0 |  |  | Actual |  |  |  | 0
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period |  | JANUARY 2025- DECEMBER 2025
Source of Funding |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
10.Staff Training, Management and Technical Review Meetings | Plan | CR/ASDA/TS/010/25 | 12000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 12000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 12000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
11. Food Vendor Screening and Quarterly Clean up Exercise | Plan | CR/ASDA/TS/011/25 | 41000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 41000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 41000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
12. Fumigation/Disinfection and Disinfestation | Plan | CR/ASDA/TS/012/25 | 261625 | Least-Cost selection | ETC | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 261625 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 261625
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
13. Maintenance of Final Disposal Site | Plan | CR/ASDA/TS/013/25 | 14000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 14000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 14000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
14. Evacuation of refuse dumps | Plan | CR/ASDA/TS/014/25 | 40000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 40000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 40000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
15. National Day Celebration | Plan | CR/ASDA/TS/015/25 | 55000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 55000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 55000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
16. Strengthening of Sub-District Structures | Plan | CR/ASDA/TS/016/25 | 107000 | Least-Cost selection | ETC | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 107000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 107000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
17.Department of Statistics Administrative Recurrent Expenditure | Plan | CR/ASDA/TS/017/25 | 18903.16 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 18903.16 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 18903.16
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
18.Procurement and Repair of Street Lights | Plan | CR/ASDA/TS/018/25 | 30000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 30000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 30000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  | 1357625 |  |  | Plan | [7 empty] | Plan |  |  |  | 1357625 |  |  | Plan |  |  |  | 1357625
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Actual |  |  |  |  | Actual | [7 empty] | Actual |  |  |  | 1357625 |  |  | Actual
Procurement Entity |  | AWUTU-SENYA DISTRICT ASSEMBLY
Budget Period |  | JANUARY 2025- DECEMBER 2025
Source of Funding |  | GOG/DACF/IGF/DACF-RFG |  |  |  |  | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Ag | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration |  |  |  |  | Duration | 3 - 6 wks | 1 -2 wks | 4 - 12 wks | 2 - 3 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks | Duration | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Duration
19. Street Naming and Property Addressing System | Plan | CR/ASDA/TS/019/25 | 40000 | Least-Cost selection | HoE | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 40000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 40000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
20. Skills Training of MSMEs Organised by Hon. MP | Plan | CR/ASDA/TS/020/25 | 70000 | Least-Cost selection | ETC | Plan | 14/02/25 | 22/02/25 | 12/05/25 | 26/05/25 | 16/06/2025 | 23/06/2025 | 06/07/2025 | Plan | 21/07/2025 | 04/08/2025 | 18/08/2025 | 70000 | 24/08/2025 | 08/09/2025 | Plan | N/A | 11/10/2025 | 09/11/2025 | 70000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Plan |  |  |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual